HEIW Transitional Corporate Risk Register – 21 March 2019

| Ref RO | Risk Description | Inherent Risk |  |  | Mitigating Action | Residual Risk |  |  | RAG Status | Proximity | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Details of risk If…then… impact… | Impact | Probability | Overall Score | Summary of action to date or proposed action to reduce risk impact or proximity | Impact | Probability | Overall Score | R/A/G & trend direction ie ↓ ↔ ↑ or *(new) | Proximity = Black, Grey or Blue or CLOSED |  |
| 1. JR | Programme Legacy Risk If HEIW doesn’t have sufficient HR support there is a risk of delay/failure to deliver on core HR activity & appoint to remaining vacancies in organisational structure, with a consequent impact on delivery of plans and objectives. | 5 | 4 | 20 | This requires: - Additional short term HR capacity to be secured by HEIW to support the initial peak in recruitment & HR activity over the next 6 -12 months - Both NHS and Agency options to be considered - Substantive recruitment to be progressed to HR roles asap. Prioritisation of work for People team including recruitment activity. | 4 | 3 | 12 |  |  | Substantive recruitment to permanent HR roles is being progressed; selection of managers have been trained to undertake online recruitment processes and/or be panel members; one additional temporary member of staff recruited Internal job evaluation panels commenced in March and will run regularly in the coming months with support from staff representatives Prioritisation agreed, regular meetings in place with Head of People & OD Team. |
| 2. DN | Programme Legacy Risk If HEIW does not have core finance capacity, including appropriate support on financial processes, through Shared Services, there is a risk of lack of compliance with financial duties, SOs and SFIs and the ability to meet statutory financial requirements. | 5 | 3 | 15 | This requires: - Senior finance roles to commence asap - Interim capacity solutions to cover other roles - Permanent finance roles to be recruited to by December 2018 (link to Risk1) - Financial Shared Service SLA to be reviewed. - Close working with Welsh Government and Wales Audit Office to ensure priority areas are covered. | 5 | 2 | 10 |  |  | Deputy Finance Director and Head of Financial Accounting now in post Recruitment underway to other permanent Finance posts. Additional temporary resources brought in from December, to support high workload areas. Deputy Finance Director working closely with the Welsh Government & Wales Audit Office on priority areas. |
| 3. JR | Programme Legacy Risk If full ESR & e-expenses functionality are not available to the organisation from launch then there is a risk of additional workload and difficulties in producing performance information | 4 | 4 | 16 | This requires: - Additional capacity to be secured to administer paper based systems - Continue to work with NWSSP to overcome barriers to access - Clear timescales for full functionality to be agreed | 3 | 4 | 12 |  |  | Additional capacity secured. NWSSP indicating imminent roll-out of e-expenses. Prioritisation of ESR build and decisions on hierarchies have been agreed, as well as clarity on timescale expectations. |
| 4. DN | Programme Legacy Risk The Legacy functions transferred to HEIW, did not include an IM&T function. If HEIW does not have the appropriate IM&T structure in place, it will not be able to deliver on key IT compliance and security priorities, e.g.: Complying with NWIS SLA; IT security updates; Supplier Licences (Microsoft/ Phones). | 4 | 4 | 16 | This requires: - Liaison with the Welsh Government to highlight this legacy gap in the HEIW staffing structure. - Close working with NWIS to identify the IM&T staffing gap and update the HEIW staffing structure. - Seek additional funding from the Welsh Government to fund these key IM&T posts. - Commence recruitment process for Head of Digital/ IM&T in November. - Bring in interim resources to support capacity challenges. | 3 | 3 | 9 |  |  | We have liaised with Welsh Government & NWIS to identify IT gap and confirm funding for these posts within the HEIW staffing structure. Interim arrangements in place to cover the management responsibilities of the vacant head of digital post as well at temp staff in place for 2 of the 3 IT posts. |
| 5. DN | Programme Legacy Risk If HEIW does not have appropriate H&S expertise and processes in place, it will not be able to deliver on key H&S compliance requirements. | 5 | 4 | 20 | This requires: - Planning and Corporate Services Team to deliver a H&S Framework. - Fire Risk Assessment has been undertaken. - HEIW has commissioned a H&S Gap Analysis. - HEIW currently commissioning an external consultant to act as HEIW’s competent H&S lead until substantive arrangement are in place | 3 | 3 | 9 |  |  | An external consultant, has been engaged to act as HEIW’s competent H&S lead and has commenced the development of essential HEIW H&S policies. The HEIW Facilities and Compliance Manager is working closely with the external H&S consultant to strengthen the HEIW H&S compliance requirements. |
| 6. DB | Programme Legacy Risk If HEIW does not have appropriate Data Protection expertise in place, it will not be able to deliver on key requirements of the Data Protection Act 2018. | 5 | 4 | 20 | This requires: Review of compliance with Data Protection identified: - Data Protection support and expertise did not transfer from legacy organisations to HEIW; - legacy organisations did not fully implement plans for compliance with GDPR; - HEIW seek additional funding from WG for a FT GDPR; - HEIW second a GDPR officer to provide us with the required expertise. | 4 | 3 | 12 |  |  | GDPR officer has been seconded from Shared Services on a PT basis from 8 January. GDPR officer to commence the development of policies and procedures to ensure compliance with GDPR. Additional funding for a FT GDPR role sought from WG. WG have refused to provide additional funding for the GDPR role; role being supported from the core HEIW budget. |
| 7. AH | Programme Legacy Risk If the interface with Welsh Government is not clear there is a risk to the delivery of HEIW functions and potential for confusion | 3 | 4 | 12 | This requires - Ongoing development and clarification of the interface with WG policy leads in writing/handover document - Regular update meetings between HEIW and WG to share issues and lessons learned - Clear actions regarding remit letter. | 3 | 3 | 12 |  |  | Monthly catch up meetings in place with WG lead to update on interface issues Monthly 1;1 meetings with Andrew Goodall Clear accountability framework now received |
| 8. DB | Programme Legacy Risk Under transfer and transitional agreement HEIW liable for funding shortfalls in the Pension Schemes. This would arise where there is any bulk transfer shortfall if there is a bulk transfer exercise from the CU Pension Schemes to the HEIW pension arrangements. | 4 | 5 | 20 | Welsh Government have provided verbal assurances that they will provide financial cover for this risk. We are requesting that these assurances be confirmed in writing by Welsh Government. | 3 | 4 | 12 |  |  | Clarification still awaited from Welsh Government. |
| 9. JR | Programme Legacy and Business Continuity Risk If the communications and engagement programme has not been effective there will be a breakdown in communication with stakeholders following launch and potential disruption to business as usual | 5 | 2 | 10 | This requires - Ongoing implementation of the agreed engagement plan with regular monitoring by Executive Team - Targeted communications for frequent service users about changes in contact details | 5 | 2 | 10 |  |  | Draft plan in place from August 2019. Activity continues within a fairly regular cycle, however the risk remains as we are still a new organisation. Formal Strategy to be considered by HEIW Board in March 2019, for implementation in April 2019. |
| 10. JR | Programme Legacy and Business Continuity Risk If the work on values and behaviours is not sustained there will be an impact on the culture of the organisation. | 4 | 4 | 16 | This requires: - Development of an implementation plan. - Regular discussion about values and behaviours with staff. | 3 | 4 | 12 |  |  | Progress has been impacted by the operational issues which have required prioritisation. However there has been regular reinforcement of the values work eg at the staff event in December and development of draft individual performance system. Senior OD practitioner took up post on 14th Jan; network of culture champions met for the first time in early March. |
| 11. AH | Business Continuity If the work associated with the transition to HEIW and the new opportunities/expectations cause a distraction and additional work for staff there is a risk to delivery of 18/19 work programme, | 4 | 4 | 16 | This requires: - Clear and realistic remit letter to be agreed and communicated - This is linked to the mitigation for Risk 1. - Consolidation of remaining work plans for 18/19 into a clear plan for oversight by Executive Team and Board | 3 | 3 | 9 |  |  | Remit letter has been received and work allocated. Regular updates received on work plans. |
| 12. PM | Core Business If the medical trainee recruitment process doesn’t achieve a good fill rate then this will have a serious impact on service delivery in the NHS and credibility of lead organisations | 4 | 5 | 20 | HEIW as new organisation able to increase promotion of the ‘Wales offer’ and the ‘Product’ and differential Wales has to offer • Train, work, Live. • Education Contract • Quality of training • Leadership & academic opportunities • More engaging use of social media to generate marketing research information • Review Service/training expectation Increased presence at Careers Events Bring national meetings to Wales Explore cross deanery arrangements Increased College engagement in Wales Support changes to workforce planning to revise service models and use of other professions if trainee doctors cannot be recruited in certain specialties. | 3 | 4 | 12 |  |  | Regular ongoing dialogues and discussions with Health Boards around those high risk specialties. Fill rates following round 1 will be distributed to Health Boards and stakeholders at the end of March. Where applicable contingency plans will be discussed based upon confirmed fill rates and predictions for Round 2. Plans developed to increase intake for GP trainees for August 2019 and to introduce a revised method for delivery of the GP curriculum moving to a 1 year in secondary care and 2 years in GP. This model is more attractive to trainees. |
| 13. DN | Core Business: HEIW Recurrent Funding If HEIW do not have the appropriate recurrent funding levels, there is a risk HEIW will not be able to deliver on its key strategic priorities. | 5 | 3 | 15 | This requires - HEIW Director of Finance working closely with the Welsh Government to update the HEIW 2018/19 indicative baseline budgets. - Finance & Executive Teams working collaboratively to review the 2018/19 baseline budgets. - Finance to provide regular updates to the Board. - HEIW Director of Finance to continue collaborative work with the Welsh Government to ascertain appropriate recurrent funding. | 4 | 2 | 8 |  |  | We are working closely with the Welsh Government to update the 2018/19 indicative budget baseline WG have confirmed our recurrent baseline for future year funding. Updates on the budget baseline exercise and financial issues are being reported to Executive Team and the HEIW Board. |
| 14. SG | Core Business If there are changes to the NHS bursary system this could affect commissioning of education for students and reliability of workforce plans and projections for 20/21 onwards | 4 | 3 | 12 | Provide ongoing advice to WG following closure of consultation Develop contingency plan for a range of possible scenarios which could result from the outcome of the consultation. | 4 | 2 | 8 |  |  | Still awaiting outcome from WG following the consultation (27.12.2018). |
| 15. PM | Core Business In 2019 the GMC intend to publish Differential Attainment data for each Deanery across the UK which could have an impact on the reputation of medical training in Wales and recruitment. | 4 | 4 | 16 | This requires - Early review of data and understanding of key messages - Consult with NHS Education Scotland on the progress there. - Use Scottish Action plan as Wales Template - Immediate focus on quick corrective actions - Development of robust action plan to accompany any publication of this data by GMC - Escalation of issue to Health Boards via MDs as key partners in delivery of medical training. - Escalation of issue to WG and for information | 3 | 4 | 12 |  |  | Wales DA data has been considered extensively and shared with Specialty Schools for discussion and local action planning at a specialty level. Specialties are now aware of their hotspot areas and are considering ways to address to address these. The Differential Attainment Implementation Group held it’s initial meeting at the end of January. We are developing a suite of current support offered to trainees coming into wales from abroad and bespoke support offered to all trainees. Wales will also be part of a GMC commissioned research project looking at Differential Attainment in Core Psychiatry, Core surgery and Paediatrics. |
| 16. PM | Core Business If the new Internal Medicine Training (IMT), Shape of Training curriculum is implemented without sufficient engagement with the NHS it could affect service delivery | 4 | 4 | 16 | This risk will heighten in 2 years’ time when the new third year of the Core Medical Training will materialise. A robust programme approach engaging the NHS and a robust programme plan with HEIW Executive leadership and regular reports into Executive Team All Wales workshop hosted by the WD on 27 June 2018, with attendees from across the sector. Plan for further workshops Nationally in UK and Wales. Work underway with IM leads and specialties to identify capacity to over-recruit in 2020 to minimise the impact. Further consultation with HBs and finance leads required to collaborate and underwrite the financial risk. Particular focus will be on creating new attachments to Intensive Care Medicine. | 4 | 3 | 12 |  |  | Significant discussion and preparation with NHS Wales has already taken place. All the Health Boards have appointed Internal Medicine Leads. Update meetings with IMT leads take place every 2 months to explore issues, share best practice and address and questions Health Boards may have with the next meeting scheduled at the end of March. The focus of this meeting will be on contingency planning following completion of Round 1 recruitment. Engagement established with GMC/RCP. Effective links established with workforce planning process re additional posts to ensure inclusion in 2019 and agreement by HBs/WG. |

| 17. JR | Core Business If BREXIT deal impacts on right to work in UK, visa processes and Numbers this will impact on current and future trainees (137 (2.9%) of trainee work force is EEA and 565 (12%) IMG as of 30 August 2018) | 4 | 4 | 16 | This requires: - Continued monitoring of Brexit discussions and impact on NHS until outcome is known - Assess impact on trainees from EU - Early development of action plans to respond to outcome of deal - Early communication with Health Boards, GMC, WG and the Royal Colleges. | 4 | 3 | 12 |  |  | No change to risk status. Continuing to attend Brexit Ministerial Group and to participate in exercises and requests for action. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 18 PM | Core Business If Post Graduate Medical Education Quality Management issues are not addressed effectively this could lead to increased intervention by GMC and an impact on trainees and patient care. . | 4 | 3 | 12 | This requires - Regular action Quality Management reports to Executive Team - Regular planned and ad hoc communications and dialogue with MDs, AMDs (Ed), LFLs College tutors, TPDs and HOSS. - Support for LETBS in terms of action planning and development of solutions - Escalation of major concerns to MDs and CEOs for attention via HEIW MD and CEO - Further escalation of major issues to the WG | 3 | 3 | 9 |  |  | The QM Dashboard has been modified to match the risk matrix of the NHS Health boards. Monthly monitoring and close working with Health Boards continues. The Board has received a comprehensive paper on the quality management process for Post Graduate Medical Education Annual Commissioning visits to all HBs is almost complete. Wales is a pilot site for the testing of a revised GMC quality assurance process which will include more direct observation of governance in action and a self-declaration by HEIW. |
| 19. SG | Core Business The introduction of the streamlining project by NWSSP could adversely affect student recruitment into the health sector in Wales and while this is not being managed by HEIW if this is not successfully implemented it could cause reputational damage. | 4 | 3 | 12 | This requires - HEIW team advising the implementation group - HEIW advising DON, W&OD Directors and COD and providing a link between the various parties | 3 | 3 | 9 |  |  | Ongoing discussions with relevant peer groups and stakeholders |
| 20. | Programme legacy – NEW RISK If there is a further delay to securing pensions advice for staff who have been subject to TUPE it could impact on the ability of staff to make informed choices about whether to opt out of the NHS pension scheme, and HEIW could be in breach of the commitment made by WG as part of the TUPE process. | 5 | 4 | 20 | This requires: - HEIW urgently to secure a service provider, in dialogue with NWSSP procurement team. - Timely access to advice, to ensure decisions can be made 3 months prior to the anniversary of enrolment – ie July 2019 | 4 | 4 | 16 |  |  | Following the unsuccessful tender process in late 2018, we had worked with Government Actuaries Department as a potential supplier. In February, the option to use GAD fell through so we have been urgently exploring alternative options. A potential supplier was identified to us but has failed to respond to our requests for confirmation in the past week, after initial exchanges were positive. An escalation meeting will be held w/c 25th March to determine next steps, following which a briefing update will be provided to staff. This continues to be an urgent priority. |

Where proximity is to be included, the following should be used:

| Black | Short Term (0-3 Months) |
| --- | --- |
| Grey | Medium Term (4-12 Months) |
| Blue | Long Term (13 months+) |

Risk Scoring Matrix

| LIKELIHOOD | Probable | 5 | 10 | 15 | 20 | 25 |  | Level | Colour | Score Range |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Likely | 4 | 8 | 12 | 16 | 20 |  | Low |  | 1 – 6 |
|  | Possible | 3 | 6 | 9 | 12 | 15 |  | Moderate |  | 7 – 14 |
|  | Unlikely | 2 | 4 | 6 | 8 | 10 |  | High |  | 15 – 25 |
|  | Rare | 1 | 2 | 3 | 4 | 5 |  |  |  |  |
|  |  | Negligible | Minor | Moderate | Major | Critical |  |  |  |  |
|  |  | IMPACT |  |  |  |  |  |  |  |  |