National Diagnostics Programme

WORKFORCE PLAN

January 2024

V .07 Final Draft. January 2024

V.02 for HEIW Executive Team July 23

Version 0.1

| CONTENTS | Page |
| --- | --- |
| Introduction | 3 |
| National Diagnostics Transformation Programme | 4 |
| Current Position: National perspective | 4 |
| Key Risks and Issues | 6 |
| Key Actions 2023-25 | 8 |
| Workforce Plan Table of actions | 9 |
| Development of a Strategic Workforce Plan: - Pillar 1 - Workforce Intelligence - Pillar 2 - Horizon Scanning/Strategy Mapping - Pillar 3 - Engagement | 17 18 27 28 |
| Governance | 30 |
| Conclusion | 30 |
| Appendices: |  |
| - Summary of available workforce intelligence | 31 |
| - Summary of additional key workforce actions 23-25 - Imaging - Endoscopy - Pathology - Genomics - Healthcare Science | 36 39 43 47 49 52 |
| - Summary of Health Board IMTPs: Key Diagnostic Issues and Actions 2023/24 | 56 |
| - Strategy Mapping and Horizon Scanning | 67 |

INTRODUCTION

In April 2023, Welsh Government published a Diagnostic recovery and transformation strategy for Wales covering the period 2023 to 2025.  The strategy recognises that diagnostic services are a fundamental aspect of modern healthcare delivery and that large backlogs of diagnostic procedures hold NHS Wales back from making improvements in referral to treatment times, impair screening pathway effectiveness, result in poor patient experience, and have the potential to result in harms and poorer outcomes.  Diagnostics are an essential component of nearly all pathways and provide the evidence on which clinical decisions are made.  Diagnostic capacity in NHS Wales does not currently meet the demands on the service and workforce shortages are a significant factor.

The key objectives of the Strategy are to:

- Improve outcomes and reduce pressure on secondary care

- Address unmet care need that has been exacerbated by COVID-19

- Enable people to live longer, healthier lives at home

- Identify, intervene, and manage disease more rapidly and at an earlier stage

- Create a sustainable and intelligent, integrated health system which reduces inequality

- Make Wales a great place to live and work

The Strategy sets out a number of key priorities including:

- Creating additional diagnostic capacity

- Moving to a combined approach of diagnostics as a whole

- Providing more directional national leadership for NHS Wales through the National Diagnostics Board

- Establishing a dedicated National Diagnostic Transformation Strategy as part of the NHS Wales Executive

- Expediting transformation in diagnostic service models

NATIONAL DIAGNOSTICS TRANSFORMATION PROGRAMME

The National Diagnostics Programme was established to oversee the delivery of a transformation programme for diagnostics services in Wales following the publication of  Our programme for transforming and modernising planned care in Wales and reducing the waiting lists (gov.wales).  The Diagnostics Programme is now overseeing delivery of programmes including pathology, endoscopy, imaging, genomics, and healthcare science.

The objectives of the programme are set out below; almost all objectives have a workforce component:

- Increase the training pipeline and roll out the multi-professional Academy model in other disciplines

- Expedite transformation models and plan for less complex diagnostics closer to home

- Provide regional diagnostic hubs and invest in upgrading facilities to meet accreditation standards

- Test emerging technology and accelerate scale up across Wales

- Create an environment for collaborative working across organisational boundaries

- Integrate and digitise all test requesting and reporting and adopt innovative digital solutions using AI

- Ensure all diagnostic services gain accreditation

- Develop safe and sustainable asset management

- Develop national service specifications setting out expected standards across all disciplines

- Develop sustainable services that have the workforce capacity to meet future need

- Increase the speed of diagnostic testing and reporting to 8 weeks

In 2022, the National Diagnostics Programme asked HEIW to support with the bringing together of existing workforce plans being taken forward within specialist areas to form a strategic workforce plan for diagnostics.  It was agreed that this work would start in the final quarter of 2022/23 and that a plan would be developed in 2023/24.

CURRENT POSITION: NATIONAL PERSPECTIVE

Significant work has already been undertaken within NHS Wales on workforce issues.  Prior to the establishment of the national programme, a number of individual service-focussed programmes were operational under the auspices of the NHS Wales Collaborative and each area has established a dedicated workforce enabling /transformation project or workstream.  These include:

- National Pathology Programme

- National Endoscopy Programme

- National Imaging Programme

Separately, Genomics Partnership Wales is hosted by Cardiff and Vale University Health Board and focusses on the potential of genomics to improve the health, wellbeing, and prosperity of the people of Wales in line with the UK Genome Strategy and the Welsh Government Genomics Delivery Plan.

HEIW manages the National Healthcare Science Programme, published by Welsh Government in 2018, which has responsibility for driving forward the national strategic framework for all professions within Healthcare Science.  Diagnostics developments include joint work with the Imaging, Pathology and Genomics Programmes in relation to the healthcare science workforce within those service areas.  The Healthcare Science Programme also leads on workforce developments across Clinical Physiologies, Medical Physics and Clinical Engineering, and Radiotherapy, linking in with relevant Networks and Advisory Committees.

There is a separate programme covering the development of Position Emission Tomography (PET) being led by the Welsh Health Specialised Services Committee (WHSSC) which links to the investment in additional PET facilities in Wales.  There is a workforce group that HEIW chairs, and recommendations on future workforce models will be considered through specialist services commissioning arrangements.

The Diagnostics Programme recognises the good foundations that have been put in place through these individual programme approaches.  The creation of the NHS Executive provides an opportunity to improve joint working across individual programme areas and with HEIW.  This helps to avoid fragmented approaches to delivery, reduce duplication, better align national and local approaches and to ensure alignment with the Health and Social Care Workforce Strategy.

Over the last 12 months, significant progress has been made in workforce development within individual programmes and it is clear that there is an appetite for collaborative working across programmes, Health Board footprints and in collaboration with the NHS Executive:

- National strategy for developing a Radiology Workforce model for Wales in place and approved through National Diagnostics Board

- Draft Strategy to Develop Pathology Workforce Sustainability, Training and Education in Wales which is in the process of being finalised

- Significant work to re-shape endoscopy training with approved business case for phase 1 Academy development to accelerate education & training pathways being progressed through the Endoscopy Education and Training Management Group (ETMG) and supported by HEIW

- Initial scoping of a multi-professional pathology training academy model for Wales and the development of ‘grow your own’ approaches across Wales

- Large scale change programme within Healthcare Science with additional investment into the education and training pipeline and developments underway across all pipelines and career pathways

- Work to scope a genomics workforce plan to align with the Genomics Delivery Plan, and initial progress made in securing additional clinical leadership and establishing education programmes that address the learning needs across the wider workforce

- Initiatives around workforce recruitment and retention

A particular strength is the significant level of clinical engagement and enthusiasm for change across all programme areas.

KEY RISKS AND ISSUES

The key themes identified at a national and local level are:

- All diagnostic services under significant pressure across Wales

- Increased demand for diagnostics as well as increased complexity of tests in some areas

- Insufficient capacity having a detrimental effect on patient experience and outcomes

- Plans for increase in diagnostic capacity with Community Diagnostic Hubs in development across neighbouring areas but lack of a sustainable workforce pipeline for the future

- Difficulties in recruiting to healthcare science roles, particularly in radiography, clinical physiology (cardiac physiology, respiratory physiology, neurophysiology, audiology), medical physics, clinical engineering, biomedical sciences & Genomics (this will be looked at more closely in the Genomics workforce plan)

- Cardiac and respiratory and sleep physiology are small workforce groups and there is increasing pressure and need to deliver services in both secondary care sites and in the community

- Key risks from lack of national digital infrastructure, for example, digital cellular pathology which both hampers new workforce models but also impacts on the delivery of core education and training (as pathology training examinations migrate to digital platforms)

In terms of workforce risks, some common risks have been identified, it is worth noting that these are issues also highlighted in other parts of the UK:

- Lack of work-based placement capacity, particularly for training of Diagnostic Radiographers, Cardiac Physiologists and Biomedical Scientists

- Lack of capacity and skills sets within organisations to deliver training and education or to provide the mentorship/ supervision required to support staff career progression/ training the future workforce.  The need for investment in an appropriate training infrastructure and key roles such as Practice Education Facilitators has been identified

- Ageing workforce leading to a loss of experienced staff impacting across all disciplines

- Pressures on the workforce which are leading to low morale; changes in retirement patterns; movement to roles in England; a negative impact on the well-being of the workforce and people opting to leave permanent roles in order to reduce work intensity and/or improve work-life balance with an increase in agency working

- High workforce vacancies/sickness in some areas impacting the ability to deliver services, further compounding the challenges in releasing staff for training and development

- Increasing reports of burnout amongst both medical trainees and trainers, particularly in diagnostics services posing significant risk to the quality of training and the pipeline of medical Consultants national-training-survey-2023-initial-findings-report.pdf (gmc-uk.org).

- Competitive roles outside of NHS Wales offering agile working coupled with incentives such as London weighting and Recruitment and Retention Payments (RRP) causing a significant threat to service delivery in Wales and impacting on key areas (such as clinical scientist roles); risks that an expansion of new service models such as diagnostic hubs in England will draw staff from Wales particularly in border areas that are at greater exposure

- Workforce supply risks into the future including the lack of structured career pathways and opportunities for personal and professional growth within job roles in some areas and broader factors such as an increase in Less Than Full Time (LTFT) working

The horizon scanning work also identified opportunities that need to be fully explored:

- Development of enhanced, advanced and consultant practice within the multi-professional workforce across radiography, pathology, cardiac physiology, neurophysiology and audiology and fully embedding the new enhanced, advanced and consultant level framework across all disciplines

- The implementation of ‘in service training’ through the use of practice education facilitators and more structured delivery of training and education across the multi-professional workforce

- Develop the support workforce in all areas in a way that releases capacity to allow our senior workforce to ‘do what only you can do’, recognising that these ambitions need to address long-standing challenges and break down professional boundaries

- Opportunities to better utilise digital solutions to maximise productivity and efficiency but also to support more innovative workforce models (e.g. digital cellular pathology and moving to wholesale electronic test requesting and reporting)

- The significant potential benefits from rapidly advancing science, digital and data particularly in terms of artificial intelligence and precision medicine

- Opportunities to develop improved collaboration across diagnostic services to build on our existing architecture to deliver better outcomes for patients through collaboration

- Improved education and training opportunities through collaborative working and delivery of new models such as the development of Academies with a focus on ‘grow your own’ increasing work-based learning opportunities

- Focussing on skills needed rather than roles and constructing workforce models that are adaptable to the skills needed now and into the future

KEY ACTIONS 2023-25

The following section sets out the key actions to be taken forward.  These represent a set of both strategic and tactical actions to be taken forward in collaboration with individual programme areas. These demonstrate that there is a significant overlap between individual programme areas and the potential for increased collaboration across disciplines to avoid duplication and fragmentation of effort.  Where actions are identified for 2023/24, initial scoping work will be undertaken in preparation for detailed work in 2024/25. The key actions are also subject to resource availability and capacity within national programmes and HEIW to support and may need to be prioritised.  In 2024/25 an assessment will be made of the need for continual focus on the areas and the potential need for work to continue into 2025/26.  Key priority areas identified by the individual programme areas are set out below.  (Further detail on the specific actions is included at Appendices 2a to 2e).

Summary of Priority Areas across Imaging, Pathology, Endoscopy, Genomics & Healthcare Science Programmes

| Workforce priority | Description of key area | Pathology | Endoscopy | Imaging | Genomics | Healthcare Science |
| --- | --- | --- | --- | --- | --- | --- |
| Workforce Planning | Training and upskilling; improvement in data quality, improved ability to forward plan; development of strategic workforce plans | (Draft) |  | (Plan in place) |  |  |
| Recruitment & Retention | Career development; career pathways; attraction campaigns; retention initiatives |  |  |  |  | ✔ |
| Education, Training and Development | Development of Academy models that meet the needs of the multi professional workforce to enhance education and training |  |  | (Academy in place for medical workforce) |  | (Developments with the NSHCS) |
| Workforce development | Exploring advanced & consultant level practice, development of support worker models; standardisation of roles etc |  |  |  |  | ✔ |

Across the individual programme areas and within HEIW there are a number of actions that are part and parcel of core work programmes which will be focused on within available resources and capacity. These actions are detailed in Appendix 2 and will be tracked and monitored through existing governance arrangements.

In addition, formed through the engagement process and in conjunction with individual programme areas, there are other actions that are more strategic and transformational in nature and are included below. These actions are expected to deliver the most significant benefits for NHS Wales and will be tracked as part of the delivery of this plan and reported through the Diagnostics Strategic and Operational Group (DSOG).

| Strategic and Transformational Workforce Actions |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Theme: Attraction & Recruitment |  |  |  |  |  |  |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 1.1 | Implement the Healthcare Science Apprenticeship Framework to increase the number of apprenticeship routes. Promote accredited part time delivery qualifications to support diagnostic services across Wales | HEIW | Provide alternative routes into the profession. Encourage ‘grow your own’. Improve retention of staff. | Numbers of apprenticeships available; number of apprentices in post; retention of apprentices into roles |  |  | All |
| 1.2 | Increase the number of commissioned part time degree courses and practitioner qualifications to widen access into roles including from existing workforce (* subject to approval of the Education & Training Plan) | HEIW | As above. | Numbers and output into pipeline |  |  | All |

| 2. | Theme: Seamless Workforce models |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 2.1 | Develop a learning progression pathways framework from level 2 through to level 7 for diagnostic services | HEIW/ Programmes | - Promote destination careers with ability to join and jump off at a number of points. - Clear career pathways for staff and HB’s. | Qualitative assessment |  |  | P, I |
| 2.2 | Review the 7-day working pilot in Cellular Pathology in C&VUHB to learn lessons nationally | Pathology Programme | Better understand scope of 7 day working in Pathology. Share lessons learned | As set out in pilot |  |  | P |

|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 2.3 | Defining multi-professional roles and maximising the contribution of the whole team within diagnostic services: - Develop standardised job title/roles and descriptions that are used nationally and work with HBs/Trusts to ensure adoption and create a repository for sharing (Aligning with work being undertaken in the Welsh partnership forum workplan under the pay agreement for 2023/24) - Leading the sharing of examples and embedding a core set of support worker roles across Wales with appropriate skills mix/ratio of support worker to registrant especially in areas with registrant recruitment difficulties - Identify core JD’s for flexible workforce roles that can span disciplines (working with Workforce & OD Directors) - Develop All-Wales Standardisation of Practice documents for Band 4 Assistant Practitioners within diagnostics that provide a common understanding of where a Band 4 Assistant Practitioner role could add value within the different disciplines - Review existing Level 4 Assistant Radiographic practice qualification to ensure that it is fit for purpose and has equitable access for all Health Boards/Trusts across Wales | HEIW/ Programmes | - Standardised titles/JD and banding to minimise perceived inequalities between HB’s. Highlight opportunities to maximise HCSW value and plug workforce gaps safely and effectively. - Formalise and promote roles between traditionally siloed disciplines to maximise value - Ensure Assistant practitioners are working at top of licence with defined competencies/standards. Increase capacity of B5/6 staff to work more efficiently/effectively. | - Change in skill mix ratios - Number of training opportunities provided for the support workforce |  |  | I, P, E I |
| 2.4 | Improve Workforce Planning across Diagnostic services: - Ensure that all local workforce plans are completed on an annual basis in a standardised template to enable effective regional and national workforce planning and align with the IMTP process to build workforce planning capacity and capability within services - Introduce a collaborative approach within diagnostics services to review intelligence from organisational workforce plans to identify key areas of workforce options and solutions | HEIW/ HBs/Trusts | - Improve accuracy of data used for IMTP/ETP planning. Align process so standardised information can be easily compared nationally - Enable sharing of good practice and enable regional workforce solutions - Sharing of good practice and providing support i.e. regional solutions for more specialist and difficult to recruit to roles. | Qualitative |  |  | All |
| 3. | Theme: Workforce Supply and Shape |  |  |  |  |  |  |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 3.1 | Develop accurate metrics for the Diagnostic workforce from national to local level for: workforce capacity (numbers); skill mix and turnover (exit data) via ESR developments | HEIW and Programmes | Improvements in baseline data and therefore a deeper understanding of local and national workforce issues | Improved accuracy of information in ESR |  |  | All |
| 3.2 | Develop a demand model that will support longer term projections for the development of the diagnostics workforce over a 5-year period to inform future education and training commissioning plans and underpin IMTP projections | HEIW/ Programmes/HBs/Trusts | More accurate forecasting of service need to improve effectiveness of planning and commissioning. | Qualitative assessment |  |  | All |
| 3.3 | Work with HBs and Trusts to develop organisation level plans that support the training and recruitment of trainee posts, enabling them to accommodate the increased number of trainees and maximising recruitment of Welsh students and trainees within NHS Wales and inform HEIW of required resources for any additional posts or additional learning needs/skills/competencies | HEIW/ Programmes/HBs/Trusts | Maximise results of commissioning process by ensuring that trainees can be accommodated and that positions are available upon graduation, keeping resource in Wales. | Unfilled posts/ graduates unable to find employment |  |  | All |
| 3.4 | Genomics: - Develop Genomics Workforce Plan to identify specialist workforce requirements for genomics - Roll out new genomics literacy education & training and assess need for further resources and support to embed genomics within mainstream services | HEIW | Support the growth and understanding of Genomics. Ensure capacity is available as expansion and advances within the service develop at pace. Ensure Genomics and wider workforce have access to appropriate training to support the advances in this field. | To be agreed as part of development of plan |  |  | G |
| 3.5 | Increase pipeline of staff through education and training route for 2024/25 particularly in science areas including additional funding for equivalence routes (*subject to approval of Education & Training Plan) | HEIW | Larger cohorts of graduates to plug workforce gaps. Enable HB’s to ‘grow your own’ through equivalence routes. | Numbers and output into pipeline |  |  | All |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 3.6 | Workforce Models: - Identify optimum workforce models, roles and skill mix to maximise MDT working and make best use of existing roles - Review need for new roles in key areas where there are opportunities to develop new workforce/service models | HEIW | - Provide aspirational goals and structured approaches to effective MDT working. - Identify opportunities to develop non-traditional roles that engage staff and provide a more seamless service for patients - Ensure staff are working at top of licence and identify opportunities to make use of skills in other areas where appropriate. | Qualitative assessment |  |  | All |
| 3.7 | Increase workforce supply through enhanced, advanced and consultant practice: - Embed new Enhanced, Advanced & Consultant Practice Framework within Diagnostic services and define and offer education to support extended practice at all levels - Identify where non-medical Consultant roles could be introduced to release senior decision makers and identify supervisory responsibilities for others in the MDT - Develop an All-Wales Standardisation of Practice for Advanced and Extended Practice with associated education and training requirements identified including timescales | HEIW/ Programmes | - Ensure staff and Organisations are maximising the use of advanced/extended practice. Ensuring equitable development of pathways nationally. - Improve options for career progression and release capacity | Numbers working at enhanced, advanced and consultant level |  |  | All |
| 3.8 | Work with NHS organisations to assess the impact of regional working including new service models on future workforce requirements in terms of training pipelines | HEIW/ Programmes | Understand models of regional working e.g. insourcing/ outsourcing and track potential pipelines for the future | Clear assessment of requirements within Education & Training Plan |  |  | All |
| 4. | Theme: Engaged, Healthy & Motivated Workforce |  |  |  |  |  |  |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 4.1 | Retention: - Promote the roll out and application of national retention guidance into diagnostic services - Improve the retention of staff through better understanding the reasons for staff leaving the organisations/profession and identify the steps needed | HEIW/ HBs/Trusts/ Programmes | Understand why people want to leave their roles and what can be done to produce environments in which they feel engaged and valued. | - Turnover rate - Leaver rate - Staff survey data - Exit interview data |  |  | All |
| 4.2 | Explore preceptorship application in healthcare science professions (Aligning with recommendations made in the Welsh Partnership Forum pay agreement for 2023/24) | HEIW | Ensure graduates, returners and new starters are appropriately supported to gain confidence and experience, enabling them to fully integrate into existing teams. | Qualitative |  |  | All |

| 5. | Theme: Excellent Education and Learning |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 5.1 | Scope and develop academy models that support the education and development of the multi-professional workforce in pathology and endoscopy | HEIW with individual programme areas | Accelerated quality education and training for key professional groups | Qualitative and Quantitative Assessment |  |  | E, P |
| 5.2 | Extend number of placement opportunities within imaging services implementing recommendations from review of placement capacity | HEIW/ Imaging Programme/ HB’s/trusts | Enable further increases in commissioning numbers to meet the service demand. | Number of work-based placements available |  |  | I |
| 5.3 | Undertake pathfinder model of Practice Education Facilitator in one area and evaluate benefits | HEIW/ Pathology Programme | Understand benefits. Potential to improve training quality, lessen the training burden for existing staff. | Qualitative assessment of benefits |  |  | P |
| 5.4 | Undertake pathfinder of a ‘slow lane’ training model in one area as proof of concept and evaluate | HEIW/ Individual Programme | Improve quality of training while reducing strain on daily operations | Qualitative assessment of benefits |  |  | To be agreed in 2024/25 |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
| 5.5 | Review pathology medical training model and identify scope to increase number of training placements | HEIW/ Pathology Programme | Increase pipeline of consultant staff to plug gaps and improve training capacity for advanced and extended practice. | Qualitative assessment |  |  | P |
| 5.6 | Develop additional training for colonoscopists to increase the supply of accredited screening colonoscopists | Endoscopy programme/HEIW | Increase pool of screening colonoscopists. | Numbers of accredited screening colonoscopists |  |  | E |
| 5.7 | Develop a business case for National School for Healthcare Science to finance an operational arm within Wales | HEIW | Improve the opportunities for improvement to HCS education in Wales | Qualitative assessment – measures to be agreed in business case |  |  | All |

| 6. | Theme: Building a digitally ready workforce |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Lead | Benefit | Potential Measures | Timeframe |  | Programme area |
|  |  |  |  |  | 23/24 | 24/25 |  |
| 6.1 | Work with DHCW & individual programmes on digital roadmap for diagnostics and impact on workforce to identify opportunities for role redesign, new roles and education and training requirements (e.g. LINC, RISP, digital cell pathology) | DHCW/ HEIW/ HBs/ Programmes | Increasing flexible working options, improving recruitment and retention. | Qualitative assessment |  |  | All |
| 6.2 | Implement a national approach to horizon scanning for innovations and improvement in technology and diagnostic equipment that would provide opportunities for workforce transformation including specific actions arising from Commission on Artificial Intelligence | Programmes | Minimise duplication of work. Share findings nationally. Collective oversite of advances and opportunities. Potential to automate processes and aid triage and diagnostics therefore improving efficiencies of existing workforce. | Qualitative assessment |  |  | All |

Alignment with recommendations from Independent Review of Diagnostics (NHS England)

The actions set out above are aligned with the findings from a review by Professor Sir Mike Richards, particularly in responding to the requirement to modernise career pathways and create a supply pipeline for diagnostics services that better matches the demands that are being placed on the service.  In total, the report made 7 key recommendations.  The following table sets out a brief summary of the key areas within the Richards’ review demonstrating how our plans align but also highlighting further work that needs doing to quantify actions particularly in respect of workforce supply:

| Recommendation from Diagnostics: Recovery & Renewal | Position in Wales | Further work needed |
| --- | --- | --- |
| Imaging: There should be a major expansion in the imaging workforce – an additional 2,000 radiologists and 4,000 radiographers (including advanced practitioner radiographers, who undertake reporting) as well as other support staff and ‘navigator’ roles. Additional training places should be provided for radiologists and radiographers and initiatives will be needed to meet demand, as well as expansion in assistant practitioner and support staff roles. | Significant increase in Radiologists being trained and increased training capacity through Imaging Academy. Increase in training pipeline over last 3 years for diagnostic radiography. Funding provided for radiographers to access education in advanced practice and reporting. | Details of the pipeline (for all staff) needs to be shared with health boards and trusts so that they can plan for the output from training over the next few years. This is particularly important in terms of imaging where there will be a considerable number of medical trainees due to complete training. Further expansions of the pipeline, particularly for Diagnostic Radiographers, could be limited by work-based training capacity. |
| Imaging: There should be an increase in advanced practitioner radiographer roles, including for reporting of plain X-rays (to a minimum of 50%); and expansion of assistant practitioner roles to take on work currently undertaken by radiographers | Some development of these roles but further work to be undertaken to explore opportunities for additional advanced radiographer roles, particularly beyond plain film reporting, in line with the release of the new Enhanced, Advanced and Consultant Practice Framework in June 2023. | Understand scope and distribution of current advanced practice within Imaging. Embed new advanced practice framework within Health Boards. |
| Echocardiography – expand number of echocardiographers and clinical scientists supporting cardiac arrythmia diagnosis, pulmonary function testing, sleep studies and blood gas analysis should be expanded. Diagnostic professionals who can ‘multitask’ are required to deliver spirometry, issue sleep studies, ambulatory ECG and blood pressure monitoring, phlebotomy and point of care testing | The number of echocardiographers trained in Wales has increased however, there have been challenges in securing sufficient roles for new trainees as a result of the expansion in the programme. Publication of consultant clinical scientist guidelines and initial discussions with cardiorespiratory services on benefit in relation to strategic leadership. | Review training for workforce in physiologies. Enable creation of consultant clinical scientist roles in physiologies. Work with Health Boards to understand why there’s a failure to offer current cardiac physiology students in Wales posts on graduation despite vacancies at Band 5 level within establishments. |
| Pathology- Expand the pathology workforce, specifically histopathologists, advanced practitioners and other healthcare scientists, with an emphasis on skill mix. The establishment of training academies/schools should be considered | The number of healthcare science posts has increased and more flexible routes to training have been introduced. The provision of equivalence funding to support skill mix initiatives in 2023/24 marks a step up. Initial discussions underway on pathology training academy. | Progress training academy discussions. |
| Genomics: The number of genomic scientists and medics should be expanded and developed in line with the national genomic programme requirements, especially in cancer. The broader healthcare workforce should be developed to respond to the increased use of genomics. | There has been a small increase in the number of genomic scientists in Wales. Genomics Partnership Wales set up, with activity to promote ‘mainstreaming’ of genomics. Education in place for wider workforce (e-learning and formal modules). A Genomics Workforce Plan is being scoped. | Develop genomics workforce plan. |
| All Professional Groups: Alongside the necessary expansion of key professional groups, all relevant organisations should work together to deliver changes in the diagnostics workforce. Particular emphasis should be given to driving skill-mix initiatives across the whole country. This will require concerted action at team, NHS trust and network levels | Healthcare Science Programme in place since 2019 to ensure collaboration and ‘voice’ for all healthcare science professions particularly smaller workforce areas. | Diagnostics Programme to further enable collaborative approach. Following expected Welsh Government approval of Healthcare Science Apprenticeship Pathway for levels 2 to 4, work will be needed across services on implementation. |

DEVELOPMENT OF A STRATEGIC WORKFORCE PLAN

Methodology

We have used a methodology developed within HEIW to help us shape the workforce plan as set out below:

To align with the Diagnostics Strategy, we have framed actions around the short to medium term up to the end of the strategy period in 2025, but we recognise that medium-long term workforce planning is also a priority.

In developing this plan we are aiming to build on the work being taken forward within individual diagnostic programme areas and to identify a set of actions that align with the themes within the Workforce Strategy for Health and Care which provides the overarching narrative for the development of strategic workforce planning.

Diagnostic Services

Pillar 2:

Horizon Scanning & Research

Pillar 3

Engagement

Pillar 1:

Workforce Intelligence

Key priorities

Strategic Actions for Diagnostics 2023-2025

Work under each of the pillars has progressed and a summary of the key areas is covered below:

PILLAR 1- WORKFORCE INTELLIGENCE

Data on the workforce employed within Wales is captured within ESR.  There are significant challenges in being able to analyse data, particularly for those working within the healthcare science and diagnostic workforce.  A change to the coding of healthcare science professions was introduced in 2015 however there remains inconsistency in understanding these changes and accurate recording within ESR.  The Healthcare Science Programme have undertaken work to improve the coding of healthcare science roles (including Diagnostic Radiography) within Wales.  Changes to coding have now been agreed at a UK level and a data cleanse is being undertaken in Wales in 2023/24.  This will provide more accurate data across healthcare science roles going forward.

Data available in ESR has been extracted to provide an indication on the size and shape of the workforce, detailed in Appendix 1.  Due to the challenges noted above, job role detail is not yet suitable for use in intelligence, however, occupation codes provide a high-level analysis of the professional areas.  A further gap is that the ESR system does not currently record vacancies against establishment which is being addressed as a key action within the National Workforce Implementation Plan (NWIP).  Vacancy and establishment data is available via the finance ledger for each health board and trust and is being collated as part of the NWIP work.

The age profile of the medical workforce is a concern in a number of areas particularly where a significant number of staff are aged over 55, such as neurophysiology. This is of greater concern where there is also a significant percentage of the workforce aged over 46, as changes in retirement patterns or retention rates could have a significant impact on the sustainability of services and the ability to train future doctors.

Across healthcare sciences, the most significant areas of concern are blood science, Genomics and Medical Physics and Medical illustration, but there are other areas where the proportion of younger staff in the service may be a concern in terms of future sustainability.  The rapid growth of genomics is likely to create issues in securing sufficient training capacity to support new entrants to the profession.

This graph shows the distribution of staff across Agenda for Change Bands. It may highlight opportunities to consider the development of a consistent set of support role JDs working at bands 2/3/4 and the opportunity to do more to grow our own workforce through more flexible education and training routes.  This approach would need to be supported by an effective training infrastructure that supports all bands within the service to progress and requires an appropriate ratio of supervisors to trainees.  The data also indicates opportunities to develop extended, advanced and Consultant level roles working at 8c and above which could appropriately work autonomously within defined competencies.  There is likely to be learning to share across disciplines who have successfully introduced new roles.

Healthcare Professions Workforce Supply: Forward Look

The following table summarises the number of places on undergraduate commissioned programmes within healthcare sciences.  The plan for 2024/25 was submitted to Welsh Government in July and a final decision is awaited.   There has been an increase in the number of diagnostic radiographer training placements over the period (+16%), respiratory and sleep (+75%) and life sciences (+12%); whilst other areas have been ‘steady state’.

HEIW contractual requirements ensure that all pre-registration programmes incorporate the following elements:

- 20% of the education is Interprofessional in nature, including 4 weeks of interprofessional placements.  This helps to prepare graduates for working as an effective member of the MDT as they join the workforce.

- All students have enhanced opportunities to build leadership skills as the evidence base will be covered for the first year of the programme and opportunities to build their skills through leadership academies will be in place at levels 5 and 6 of all programmes.

- All students develop improvement projects with feedback from practice educators from level 5 and 6 onwards

- All students have enhanced opportunities to build skills in the Welsh Language and have placements delivered through the medium of Welsh.

- All HEIs must evidence engagement with widening access to education.

Table 1: Healthcare commissioned programmes

| Course | University | ETP submission year 2020-2021 |  |  | ETP submission year 2021-2022 |  |  |  |  | ETP submission year 2022-23 |  |  | ETP submission year 2023-24 $ | Planned Output^ | Planned Output^ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1st year | 2nd year | 3rd year | 1st year | 2nd year |  | 3rd year |  | 1st year | 2nd year | 3rd year | Commissioning Numbers | Summer 2024 | Summer 2025 |
| Diagnostic Radiography BSc 3 years | Bangor University | 33 | 26 | 27 | 36 | 29 | 25 |  |  | 33 | 31 | 29 | 31 | 31 | 27 |
|  | Cardiff University | 96 | 82 | 67 | 102 | 86 | 82 |  |  | 114 | 91 | 77 | 109 | 84 | 105 |
|  | Total | 129 | 108 | 94 | 138 | 115 | 107 |  |  | 147 | 122 | 106 | 140 | 115 | 132 |
| Radiology Assistant Practitioner HE Cert 1 year | Cardiff University | 12 |  |  | 12 |  |  |  |  |  |  |  | 10 | Not run – no output | 10 (assumed commission total) |
| Audiology BSc 3 years | Swansea University | 10 | 16 | 18 | 11 | 9 | 16 |  |  | 12 | 9 | 7 | 11 | 9 | 12 |
| Audiology HE Cert 1 year | Swansea University | 15 |  |  | 13 | 15 |  |  |  | 9 | 13 |  | 10 | 11 | 9 |
| Cardiac Physiology BSc 3 years | Swansea University | 24 | 22 | 26 | 23 | 24 | 21 |  |  | 22 | 16 | 20 | 23 | 16 | 22 |
| Respiratory and Sleep Science BSc 3 years | Swansea University | 8 | 3 | 4 | 8 | 6 | 3 |  |  | 10 | 6 | 5 | 14 | 6 | 9 |
| Life Science BSc (Biomedical Sciences) * 3 years | Cardiff Met University | 25 | 21 | 20 | 26 | 23 | 18 |  |  | 24 | 24 | 24 | 26 | 22 | 21 |
| Neurophysiology BSc 3 years | Swansea University | 4 | 3 | 2 | 3 | 3 | 2 |  |  | 6 | 5 | 3 | 4 | 2 | 5 |
| Clinical Engineering BSc 3 Years | Swansea University | 4 | 4 | 3 | 4 | 4 | 4 |  |  | 4 | 3 | 4 | 6 | 4 | 4 |
| Nuclear Medicine BSc+ 3 Years | Swansea University | 2 | 2 | 3 | 3 | 2 | 3 |  |  | 5 | 3 | 2 | 6 | 2 | 5 |
| Radiotherapy Physics BSc+ 3 Years | Swansea University | 0 | 0 | 0 | 3 | 2 | 3 |  |  | 2 | 1 | 2 | 2 | 3 | 3 |

* Multiple routes available to graduate roles           $ These are the approved commissioning numbers and do not reflect actual fill rates

^ May be affected by attrition

+ Nuclear Medicine/ Radiotherapy Physics classed as one program in S20 and then separated from S21

At a postgraduate and Consultant level, there has been an increase of 14 places (35%) on the Specialist Training Programme (STP) and an increase of 2 places (+20%) on the Higher Specialist Training Programme since the 2022/2023 ETP.

HEIW also funds post-graduate and health care support worker education.  In 2023/24 over £5m was invested across these areas.  Data in terms of the allocation of this funding to support diagnostic service delivery is not routinely reported in detail to HEIW but work is underway to improve data quality in this area.

In terms of the development of the support workforce, the following qualifications will be included within the relevant apprenticeship frameworks, following successful consultation across Wales, once signed off and submitted to Welsh Government:

- Level 3 Clinical Imaging

- Level 2, Level 3 and Level 4 Healthcare Science

- The Level 4 Assistant Practitioner qualification for Endoscopy has been written, approved and resource assessment materials completed

- The level 4 Pathology qualification modules have been agreed across Wales to enable standardisation of content and progression to the commissioned Level 5 and Level 6 part time routes to registration

- The Endoscopy Academy approach has been agreed by HEIW Execs and the business case is to be developed with investment into posts within HEIW to drive the developments forward.

Medical Workforce

There has been significant investment in additional roles over the last 5 years in the number of doctors being trained in Wales:

Clinical Radiology - There are currently 95 trainees on the programme which will produce a healthy pipeline of Radiologists from 2023 with the potential for 90+ additional doctors over the next 5 years.  Health Boards need to plan for this pipeline to ensure that Wales benefits from the additional investment made into the Imaging Academy.

The majority of Health Boards in Wales are concerned about the sustainability of pathology services due to current vacancies, an ageing workforce profile and increasing demands on the service.

This is an area where there are fewer trainees with only 12 trainees on the programme and limitations that hamper the ability to expand training numbers.  Although Wales has been successful at retaining doctors over the last few years with all trainees completing training from August 2020 to July 2022 now in Consultant roles, the demands on the service and the lack of a modern digital infrastructure could hamper efforts to retain trainees in future without significant investment into digital solutions that support flexible workforce models.  There is already emerging evidence of trainees and Consultants choosing to work in areas where digital cellular pathology is embedded into the service.

There are currently 19 trainees on the gastroenterology programme, with nearly 50% of these due to complete training and become eligible for consultant roles in 2023.  The pipeline beyond that is more limited and Health Boards need to be actively considering how to accommodate those who are likely to complete training in the current year.  Historically, over the last 2 years only 50% of trainees have taken up a Consultant role in Wales.

Other

There is currently on 1 trainee on the clinical neurophysiology programme, and they are due to complete training in 2025.

There are currently 6 trainees on the Clinical Genetics programme and historic data shows that in the last 2 years both trainees who have completed training have taken up roles in Wales.  In terms of forward projections, there is likely to be 1 trainee completion in 2023 and 2025, with 2 due to complete in both 2026 and 2027.

Recommendations for Education and Training Commissioning in 2024/25

As indicated above, the Education and Training Plan for 2024/25 has been submitted to Welsh Government and a final decision is expected in December 2023. However, it is likely that HEIW will receive a ‘flat cash’ settlement for 2024/25 which will mean that commissioning numbers requested by Health Boards will be unable to be fully satisfied.

Healthcare Science: Undergraduate Recommendations

Healthcare Science: Undergraduate Recommendations

Decrease

- HE Certificate Audiology (Replaced by part-time BSc)

- BSc Respiratory and Sleep science (Meets 100% of IMTP requests)

- BSc Nuclear Medicine (No IMTP requests, however, identified need in Positron Emission Tomography (PET) workforce plan)

- BSc Life Sciences (Biomedical science) (New part time offer also now available)

- BSc Clinical Engineering (Meets 100% of IMTP requests. New part time offer also now available)

- BSc Diagnostic Radiography (Below ETP commissioning for 2023/24 and lower than IMTP recommendations for 2024/25 but increase from actual places filled in 2023/24)

NEW

- Part- time BSc Life sciences (Biomedical sciences) PTP (Practitioner training programme)

- Part time BSc Audiology (10 places)

- Part time BSc Clinical Engineering (10 places).

Increase

- BSc Radiotherapy Physics (to support PET programme)

- HE Certificate Radiography Assistant Practitioner

Maintain

- BSc Cardiac Physiology

- BSc Audiology

- BSc Neurophysiology

- BSc Radiotherapy and Oncology

Decrease

Audiological practice

Respiratory and Sleep science

Nuclear Medicine

Life Sciences (Biomedical science)

Clinical Engineering

Diagnostic Radiology (above IMTP requirements but lower than current level due to placement capacity constraints)

Decrease

Audiological practice

Respiratory and Sleep science

Nuclear Medicine

Life Sciences (Biomedical science)

Clinical Engineering

Diagnostic Radiology (above IMTP requirements but lower than current level due to placement capacity constraints)

NEW

Part- time BSC Life sciences (Biomedical sciences)

19 part time PTP and 22 standalone modules to support employee development

Part time BSc audiology (10 places)

Part time BSc Clinical Engineering (10 places).

Increase

Radiotherapy Physics (to support PET programme)

HE Certificate Radiography Assistant Practitioner

Maintain

Cardiac Physiology

Audiology

Neurophysiology

Radiotherapy and Oncology

Healthcare Science: Postgraduate Recommendations

Healthcare Science: Postgraduate Recommendations

- Increase Clinical Scientist Training Programme from 53 to 55 places recognising the need for gradual stable growth following the significant increase in 2023

- Increase Higher Specialist Scientist Training from 10 to 20 places

- Increase the equivalence route to registration with budget of £150k (increase from £140k) to support retention and succession planning through the Healthcare Science programme.  The proposal is to increase the scope of this programme to facilitate time away from essential roles.

- Increase Clinical Scientist Training Programme from 53 to 55 places recognising the need for gradual stable growth following the significant increase in 2023

- Increase Higher Specialist Training from 10 to 20 places

- Increase the equivalent route to registration with budget of £500k (increase from £140k) to support retention and succession planning through the Healthcare Science programme.  The proposal is to increase the scope of this programme to facilitate time away from essential roles.

In terms of the medical workforce, the proposals are to:

- Increase Foundation and Specialty training to develop a strong output of consultant roles over the next 5-10 years in line with projected retirement patterns and mitigate the impact of Less Than Full Time (LTFT) training

- Increase in the areas of:

  - Medical microbiology/infectious diseases

  - Pathology (2 posts)

  - Small specialities (4 posts).

Other postgraduate recommendations are to:

- Increase the number of places for medical ultrasound training from 15 to 20 reflecting need for pipeline of sonographers

- Invest in additional Genomic Medicine Modules

- Maintain 20 places for reporting radiography

- Decrease Level 7 Clinical Photography Diploma from 11 to 9 places (First cohort started September 2023).

PILLAR 2- HORIZON SCANNING/ RESEARCH

This element of the work programme has reviewed a number of key publications including material produced by Professional bodies, think tanks as well as Welsh Government policy in Wales.

One of the key publications produced in the UK is the work led by Professor Sir Mike Richards in 2020 DIAGNOSTICS: RECOVERY AND RENEWAL – Report of the Independent Review of Diagnostic Services for NHS England – October 2020. This independent review was commissioned by NHS England and although it has no formal status in Wales, the recommendations are applicable.  From a workforce perspective, the Richards review highlighted the need to rapidly increase the workforce to support the growing demand for diagnostic services.  The specific workforce recommendations are set out below:

- Expand the imaging workforce through increases in training pipeline and assistant practitioner and support roles

- Increase the number of advanced practitioner radiographer roles

- Establish Training Academies for endoscopy to expand colonoscopy with associated increase in specialist practitioners and endoscopy nurses

- Increase the number of echocardiographers and clinical scientists

- Expand the pathology workforce, specifically histopathologists, advanced practitioners and healthcare scientists with a focus on skill mix

- Development of genomic scientist roles and medics in line with national genomic planning

- Support organisations to work together to deliver changes in diagnostics workforce particular in driving skill mix initiatives across the country.

For context, the report estimated that there was likely to be a shortfall in key roles in England over 5 years of around 11,000 roles, which would equate to circa 650 roles in Wales.  It should be noted that these estimates were calculated pre-pandemic and given the post-Covid backlogs, this is likely to be an underestimate of the position.

In Wales, Statements of Intent have been produced for pathology services (2019) pathology-statement-of-intent.pdf (gov.wales), imaging (2018) imaging-statement-of-intent.pdf (gov.wales) and an endoscopy programme initially produced in 2019 WG_Label_Pantone_342 (gov.wales)National Endoscopy Programme Action Plan 2019-2023 (gov.wales)

These all reference challenges around workforce driven by increasing demands on the service and workforce gaps.  All also referenced the opportunity to enhance workforce development through enhanced training pipelines, opportunities for career and workforce development and the opportunity to modernise service models.

A summary of the documents reviewed is included at Appendix 4.

PILLAR 3 - ENGAGEMENT

To support a deeper understanding of the key issues impacting on the workforce and the identification of potential actions, two deliberative events were held in March and April 2023 with over 160 individuals from a cross section of geographical representation and professional backgrounds.

Both events were structured around a masterclass by Professor Alison Leary who shared insight into a humanistic workforce planning approach.  A video recording of the event is being transcribed and will be available on the Gwella portal.  The key messages from the Masterclass facilitated by Professor Leary were:

- The NHS is a safety-critical industry, and the workforce should be planned on basis of a precautionary principle where skilled and experienced staff are delivering front-line care, supporting the ‘rookie’ workforce to grow and develop their skills through practice experience.

- Workforce is a recurring theme in enquiries and common areas are workforce numbers; education/skill levels of staff; workload; poor leadership and workplace culture and normalisation

- Old models of workforce planning only focus on ‘work as seen’ not ‘work as done’ based on ‘activity’ models which under-represent true demand taking into account physical, cognitive, organisational and emotional effort

- In diagnostics, labour is being consumed by our proficient workforce in gap filling for others; intense workloads; delegated models requiring supervision and checking; poor/inadequate technology and zombie policies

- Good employment practices should be embedded to improve retention

Suggested solutions:

- Development of a distributed model whereby registered professionals are adequately supported by wider members of the team rather than a technical model of delegation which risks over-delegation, undermines professional autonomy, and can act as an exit trigger

- Demand modelling should take account of a wider range of factors than just activity, for example: caseload, risk, extrinsic factors, work left undone

- Develop people along the ‘novice to expert’ journey supporting individuals to become proficient practitioners; this requires practice facilitation

- Developing more structured career pathways for individuals and create destination careers at all levels, minimising terminal careers

- Embedding a 2-lane concept whereby there is a ‘main production line’ (where the bulk of operational delivery takes place with minimal training) with a ‘workforce development line’ (where the bulk of the workforce are trained).  This concept can help to create opportunities for experienced staff to work in a ‘slow lane’ setting, using their skills and experience to mentor and support others in training.  This could be an attractive option for part time and staff nearing retirement.  Periodically, there should be a cross-over of lanes, creating opportunities for others to gain teaching experience off the main production line, with those on the workforce development line maintaining their skills by spending time within front-line delivery

- Embedding quality improvement expertise and resource in diagnostic teams to facilitate productivity and effectiveness

The remainder of the workshop sessions focussed on participants identifying some of the key actions needed across 4 headings:

- Recruitment

- Retention

- Opportunities to redesign workforce models

- Education and training.

Discussions with the Directors of Therapies and Health Sciences (DOTHs) have also highlighted the potential for transformational change in the medium term citing a number of drivers for change:

- The increasing opportunities presented by digital and scientific advances which will change the shape of the workforce going forward, particularly in light of recent advances in Artificial Intelligence which is being explored in Wales through a Commission on Artificial Intelligence

- The need to develop new solutions to long-standing challenges of recruitment especially to rural areas and within smaller services particularly where digital transformation offers significant potential.  There is an appetite to move to a model whereby services are coordinated on a national basis and organised regionally to increase standardisation, improve resilience, and deliver economies of scale.

Other issues raised by DOTHs include the need to improve workforce planning and align national and local priorities in key areas to ensure that we are training the number of professionals that are needed and that jobs are available post-training to respond to the identified need.  Consideration should also be given to the current ask and the resource required to deliver ‘business as usual’ as well as implementing major new programmes such as RISP and LIMS 2.0 as well as supporting training and managing quality and accreditation requirements.  Further resources are needed to deliver on a broad range of objectives.

There remains some confusion over the interpretation and design of models outlined in the National Diagnostics Strategy and a lack of detail on the model for Community Diagnostics Hubs in Wales.  Despite this, work is continuing on a regional footprint to scope potential models and map capacity and demand so that it is clear on the capacity gap that needs to be addressed across the system. There are concerns that without additional staff, the establishment of new services will be challenging to deliver and there is a greater exposure to market forces from elsewhere in the UK as England looks to establish new models as part of their recovery programme.  There is a need to understand the models being planned at a regional level in Wales and the basis on which services will be operated (e.g. through managed service contracts).

Finally, there was recognition that Wales should be investing in areas of diagnostics which focus on early-stage diagnosis and prevention including pre-symptomatic screening, liquid biopsy, and potentially polygenic risk scores.  The pace of scientific advance is likely to increase over the next few years.

GOVERNANCE

Each of the actions in this plan will be tracked within HEIW through existing performance management mechanisms.  It is proposed that a highlight report is developed for the national Diagnostics Strategic and Operational Group on a quarterly basis so that progress can be monitored.  HEIW is a member of the diagnostic coordination group which brings together key representatives from the NHS Executive with HEIW, and this will bring an additional route to check in on progress and ensure alignment with individual programme objectives.

Baseline measures need to be identified to inform reporting and evaluation should be embedded within individual initiatives so that an evidence base can be built to inform future workforce planning.

CONCLUSION

The development of an overarching workforce plan for diagnostics is aimed at ensuring that work across individual diagnostic programmes is aligned under a single umbrella to improve coordination and reduce fragmentation but also to share learning and improve communication.  The implementation of the National Diagnostics Strategy and the arrangements that underpin the NHS Executive should facilitate oversight and support the delivery of national objectives aligned with Ministerial priorities.

​

Appendix 1

SUMMARY OF WORKFORCE DATA FROM ESR (MARCH 2023)

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists – Blood | Band 8c/8d/9 | 25 | 19.38 | 6 | 19 | 8 |
|  | Band 7/8a/8b | 276 | 262.18 | 90 | 186 | 53 |
|  | Band 5-6 | 501 | 465.30 | 173 | 328 | 44 |
|  | Band 2-4 | 503 | 427.10 | 147 | 356 | 97 |
|  | Non AfC | <5 | <5 | 0 | <5 | <5 |
|  | Phlebotomists | 289 | 190.90 | 12 | 277 | 89 |
| Healthcare Scientists – Cellular | Band 8c/8d/9 | 16 | 15.61 | 6 | 10 | 21 |
|  | Band 7/8a/8b | 158 | 151.06 | 47 | 111 | 22 |
|  | Band 5-6 | 254 | 240.09 | 77 | 177 | 15 |
|  | Band 2-4 | 281 | 264.12 | 93 | 188 | 7 |
| Healthcare Scientists – Infection | Band 8c/8d/9 | 6 | 4.11 | 5 | <5 | <5 |
|  | Band 7/8a/8b | 67 | 63.11 | 18 | 49 | 9 |
|  | Band 5-6 | 113 | 105.30 | 33 | 80 | 9 |
|  | Band 2-4 | 166 | 153.57 | 59 | 107 | 16 |
|  | Cytoscreeners | 29 | 24.59 | 6 | 23 | 6 |
| Medical | Consultant | 169 | 157.99 | 88 | 81 | 46 |
|  | Specialty Registrar | 50 | 44.60 | 18 | 32 | 0 |
|  | Other | 38 | 36.40 | 18 | 20 | 6 |
| Total |  | 2943 | 2627.41 (0.89) | 896 (30%) | 2047 (70%) | 450 (15%) |

Pathology
Genomics

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists – Genomics | Band 8c/8d/9 | <5 | 2.96 | 0 | <5 | <5 |
|  | Band 7/8a/8b | 37 | 35.23 | 10 | 27 | <5 |
|  | Band 5-6 | 99 | 95.79 | 35 | 64 | <5 |
|  | Band 2-4 | 25 | 24.09 | 7 | 18 | <5 |
|  | Non AfC | <5 | 0.86 | <5 | 0 | <5 |
| Counsellors- Genomics | Band 8c/8d/9 | 0 | 0 | 0 | 0 | 0 |
|  | Band 7/8a/8b | 6 | 3.70 | <5 | <5 | <5 |
|  | Band 5-6 | 35 | 27.20 | <5 | 32 | 8 |
|  | Band 2-4 | <5 | 2.40 | <5 | <5 | <52 |
| Medical | Consultant | 11 | 9.50 | 4 | 7 | <51 |
|  | Specialty Registrar | 5 | 4.40 | 0 | 5 | 0 |
|  | Other | <5 | <5 | <5 | <5 | <5 |
| Total |  | 227 | 208.03 (0.92) | 67 (30%) | 164 (70%) | 26 (11%) |

Diagnostic Radiology

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Diagnostic Radiographers | Band 8c/8d/9 | 10 | 9.71 | 0 | 10 | 6 |
|  | Band 7/8a/8b | 428 | 353.83 | 93 | 335 | 104 |
|  | Band 5-6 | 854 | 762.26 | 239 | 615 | 101 |
|  | Band 2-4 | 408 | 339.44 | 87 | 321 | 111 |
| Medical | Consultant | 188 | 176.70 | 120 | 68 | 37 |
|  | Speciality Registrar | 93 | 88.00 | 50 | 43 | 0 |
|  | Other | 10 | 9.47 | <5 | 7 | 0 |
| Total |  | 1991 | 1739.41 (0.87) | 592 (30%) | 1399 (70%) | 359 (18%) |

Radiotherapy

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Therapeutic Radiographers | Band 8c/8d/9 | <5 | 1.00 | 0 | <5 | 0 |
|  | Band 7/8a/8b | 104 | 93.85 | 18 | 86 | 10 |
|  | Band 5-6 | 105 | 96.57 | 19 | 86 | <5 |
|  | Band 2-4 | 12 | 10.20 | <5 | 11 | 5 |
| Medical | Consultant | - | - | - | - | - |
|  | Speciality Registrar | - | - | - | - | - |
|  | Other | 5 | 1.17 | 0 | 5 | 0 |
| Total |  | 227 | 202.79 (0.89) | 38 (17%) | 189 (83%) | 18 (8%) |

Physical Sciences

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists – Medical Physics and Medical Illustration | Band 8c/8d/9 | 18 | 17.91 | 13 | 5 | 6 |
|  | Band 7/8a/8b | 109 | 102.78 | 49 | 60 | 8 |
|  | Band 5-6 | 130 | 124.93 | 61 | 69 | <5 |
|  | Band 2-4 | 18 | 16.31 | 7 | 11 | <5 |
| Healthcare Scientists – Biomedical Engineering | Band 8c/8d/9 | 8 | 7.20 | 7 | <5 | 5 |
|  | Band 7/8a/8b | 90 | 85.94 | 70 | 20 | 28 |
|  | Band 5-6 | 146 | 142.72 | 128 | 18 | 46 |
|  | Band 2-4 | 81 | 74.93 | 59 | 22 | 35 |
| Total |  | 600 | 572.72 (0.95) | 394 (66%) | 206 (34%) | 133 (22%) |

Endoscopy

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing - Endoscopy | Band 8c/8d/9 | 0 | 0 | 0 | 0 | 0 |
|  | Band 7/8a/8b | 52 | 47.84 | <5 | 50 | 12 |
|  | Band 5-6 | 253 | 217.97 | 18 | 235 | 49 |
|  | Band 2-4 | 54 | 48.13 | 14 | 40 | 18 |
| Total |  | 359 | 313.94 (0.87) | 34 (9%) | 325 (91%) | 79 (22%) |

Cardiac, Vascular, Respiratory and Sleep Physiology

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists – Cardiac, Vascular, Respiratory and Sleep Physiology | Band 8c/8d/9 | <5 | 2.00 | <5 | 0 | 0 |
|  | Band 7/8a/8b | 179 | 161.21 | 53 | 126 | 22 |
|  | Band 5-6 | 154 | 144.02 | 44 | 110 | 8 |
|  | Band 2-4 | 97 | 75.65 | 9 | 88 | 30 |
| Medical - Cardiology | Consultant | 98 | 95.05 | 86 | 12 | 30 |
|  | Speciality Registrar | 51 | 50.30 | 36 | 15 | <5 |
|  | Other | 26 | 19.78 | 21 | 5 | <5 |
| Medical - Respiratory | Consultant | 66 | 63.21 | 40 | 26 | 13 |
|  | Speciality Registrar | 39 | 37.00 | 17 | 22 | 0 |
|  | Other | 14 | 13.00 | <5 | 10 | <5 |
| Total |  | 726 | 661.22 (0.91) | 312 (43%) | 414 (57%) | 108 (15%) |

Neurophysiology

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists - Neurophysiology | Band 8c/8d/9 | 0 | 0 | 0 | 0 | 0 |
|  | Band 7/8a/8b | 13 | 12.05 | 7 | 6 | <5 |
|  | Band 5-6 | 15 | 14.20 | <5 | 12 | 0 |
|  | Band 2-4 | 0 | 0 | 0 | 0 | 0 |
| Medical | Consultant | <5 | 3.30 | <5 | <5 | <5 |
|  | Speciality Registrar | <5 | 3.00 | <5 | <5 | 0 |
|  | Other | 0 | 0 | 0 | 0 | 0 |
| Total |  | 35 | 32.55 (0.93) | 15 (43%) | 20 (57%) | <5 (11%) |

Audiology and ENT

|  | Band/Grade | Total Headcount | Total FTE | Male | Female | Over 55 years |
| --- | --- | --- | --- | --- | --- | --- |
| Healthcare Scientists - Audiology | Band 8c/8d/9 | 8 | 6.85 | <5 | <5 | <5 |
|  | Band 7/8a/8b | 95 | 80.33 | 24 | 71 | 12 |
|  | Band 5-6 | 107 | 93.60 | 28 | 79 | 6 |
|  | Band 2-4 | 109 | 91.79 | 16 | 93 | 13 |
| Medical | Consultant | 20 | 19.05 | 16 | <5 | 5 |
|  | Speciality Registrar | <5 | 1.00 | 0 | <5 | 0 |
|  | Other | <5 | 3.10 | <5 | <5 | <5 |
| Total |  | 344 | 295.72 (0.86) | 90 (26%) | 254 (74%) | 42 (12%) |

Appendix 2

Summary of additional key workforce actions within individual programmes

These actions will be monitored by individual programme areas/organisations:

| 1. | Theme: Attraction & Recruitment |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |  |
|  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |  |
|  | Targeted campaigns through #TrainWorkLive in key areas (subject to resource assessment) | HEIW |  |  |  |  |  |  |  |  | All |  |
|  | Effective signposting of careers/training opportunities in diagnostic services in Wales through work with Careers service and using HEIW Careersville platform | HEIW |  |  |  |  |  |  |  |  | All |  |
|  | Develop and formalise opportunities for work experience/internship/student mentoring/taster sessions in diagnostics | Programmes/HBs/Trusts |  |  |  |  |  |  |  |  | All |  |
|  | Review vacancy data across diagnostic services to identify gaps in service provision for targeted initiatives (also aligns with wider retention plan and actions – Retention plan published in October 23) | HEIW/Health Boards/NHS Trusts |  |  |  |  |  |  |  |  | All |  |
| 2. | Theme: Seamless Workforce models |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |  |
|  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |  |
|  | Embed effective application of the Healthcare Support Worker Framework within diagnostics services to ensure consistency of approach | HEIW/ Programmes/HB’s |  |  |  |  |  |  |  |  | All |  |
|  | An All-Wales Standardisation of Practice for Radiographers should be in place to enable consistency across Wales for working across the different modalities and specialities | Imaging Programme |  |  |  |  |  |  |  |  | I |  |
|  | Explore sessional job planning for non-medical staff which would ensure that the extended and additional skills of the current and future workforce are more effectively utilised | Programmes/HBs/Trusts |  |  |  |  |  |  |  |  | All |  |
| 3. | Theme: Workforce Supply and Shape |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions | Lead |  | Timeframe |  |  |  |  |  | Programme area |  |  |
|  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |  |  |
|  | Make use of available digital intelligence within data warehouse to better interrogate the diagnostic workforce | HEIW |  |  |  |  |  |  |  | All |  |  |
| 4. | Theme: Engaged, Healthy & Motivated Workforce |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions |  | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |
|  |  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |
|  | Review output of staff survey with specific reference to diagnostics areas (when available) |  | HEIW |  |  |  |  |  |  |  |  | All |
|  | Improve communications to staff about career development opportunities |  | Programmes/HB/Trusts |  |  |  |  |  |  |  |  | All |
|  | Improve staff opportunities for involvement in research |  | HB/Trusts/ Programmes |  |  |  |  |  |  |  |  | All |
| 5. | Theme: Excellent Education and Learning |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions |  | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |
|  |  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |
|  | Extend opportunities for existing workforce to access equivalence funding |  | HEIW |  |  |  |  |  |  |  |  | TBC |
|  | Learn from other NHS Professions i.e. Nursing about training delivery |  | Programmes |  |  |  |  |  |  |  |  | All |
|  | Develop educator resources on a multi-professional basis using Ty Dysgu educational platform |  | HEIW/ Programmes |  |  |  |  |  |  |  |  | All |
|  | Ensure that staff are trained in emerging and new diagnostic processes, techniques, application and interpretation |  | HEIW and Programmes |  |  |  |  |  |  |  |  | All |
|  | Widely publicise all national funding streams for education and development so that they can be utilised to their full potential by organisations across Wales |  | HEIW, Programmes/ HBs/Trusts |  |  |  |  |  |  |  |  | All |
|  | Develop a reliable training data repository for tracking learners acquisition of competencies |  | HEIW/ Programmes |  |  |  |  |  |  |  |  | All |
|  | Roll out MEET (Maximising Efficiency Endoscopy Training) tool |  | E |  |  |  |  |  |  |  |  | E |
| 6. | Theme: Building a digitally ready workforce |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions |  | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |
|  |  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |
|  | Roll out digital competency framework into Diagnostic areas |  | HEIW/ DHCW |  |  |  |  |  |  |  |  | All |
|  | Review implications of new digital offer on workforce within diagnostic services, ensuring that appropriate elements are included in training. |  | Programme/HBs/Trusts |  |  |  |  |  |  |  |  | All |
| 7. | Theme: Leadership & Succession |  |  |  |  |  |  |  |  |  |  |  |
|  | Actions |  | Lead |  |  | Timeframe |  |  |  |  |  | Programme area |
|  |  |  |  |  |  | 23/24 |  |  | 24/25 |  |  |  |
|  | Work with Directors of Therapies and Health Sciences, Nurse and Medical Directors to review leadership issues in diagnostics and where focussed attention is needed to ensure succession pipeline (Aligned with the wider talent management approach) |  | HEIW |  |  |  |  |  |  |  |  | All |
|  | Ensure staff working in diagnostic services benefit from Clinical Leadership Development programme through targeted approaches/marketing |  | Health Boards/ Programmes |  |  |  |  |  |  |  |  | All |

Appendix 2a

Diagnostic Workforce Plan – Actions for 2023/24 	               Workforce Programme/Group covered:  National Imaging Programme

| Summary | Summary of key workforce priority areas for 2023/24 The key workforce priority areas for 2023/24 correspond to the four workstreams that emerged from the recommendations contained within the Strategy for Developing a Radiology Workforce Model for NHS Wales’. The Imaging Workforce and Education Transformation Group (IWETG) is responsible for the management and execution of these recommendations. A summary for each workstream area can be found below: Workforce Planning: To continue to build on the workforce planning momentum gained during the process of developing the Radiology workforce strategy and to establish the foundations of a workforce planning community for NHS Wales Radiology Services. This will include: - Delivering supplementary workforce planning training to coincide with the start of the IMTP process - Working to develop consistent and accurate workforce information that enables collection and monitoring of data on a local and national level that facilitates effective workforce planning Workforce Development and Standardisation - To identify how each staff role within Radiology services could be developed to meet requirements of current and future service needs. - Developing standardised scope of practice documents for registered and non-registered staff. - Reviewing current education and training provision against revised scopes of practice to establish where changes to content/ delivery may be advantageous and to ensure there is aligned to service needs. - To scope potential solution to training/ education capacity shortfalls within organisation i.e. explore potential for practice education facilitator roles. - To undertake a targeted piece of work to look at support for leadership development and effective succession planning in Radiology Services. Wider Imaging Workforce: - To scope and prioritise the approach to refining and repeating the workforce planning process adopted for Radiology services for other workforce groups that deliver core imaging services. To align the commencement of further strategy development for the next priority workforce areas. Medical Physics represents such an area, and we await further discussions as to whether this work will be led by IWETG (Imaging Workforce and Education Training Transformation Group (IWETG)) or we will be contributory members of a stand-alone project. - Due to a continued deterioration in the number of Breast Radiologists in Wales a task and finish group has been established to support Breast Radiology Services (Symptomatic and Screening) to develop and secure investment for a sustainable training programme for Breast Clinicians. Consideration is currently being given to the options available to facilitate the necessary training. Digital and Technological Infrastructure: - To engage with the Radiology Informatics Systems Procurement Programme (RISP) to identify opportunities for workforce transformation and to identify any workforce training requirements and benefits as a result of the deployment of a new system. - The wider Imaging Programme will also be undertaking initial scoping of the potential impact of AI on Radiology which could take account of the impact on workforce considerations. |
| --- | --- |
|  | Please outline the top 3 workforce risks that are impacting on access to or the quality of services (not HB specific) - Although the Radiographer training numbers commissioned has increased this does not necessary fulfil the resource requirements for both current and future workforce needs or take account of the future generalist/ specialist requirements of the service in support of career development - Capacity and skills sets within organisations to deliver training and education or to provide the mentorship/ supervision required to support staff career progression - The number of workforce vacancies impacts on the ability to deliver timely access to services. This is felt most acutely for hard to recruit posts or geographical locations |
| Specific workforce actions that will be taken forward in 2023/24 |  |
| Specific Actions & Milestones: Please find attached document that details actions and milestones for IWETG Priorities 2023/24. This document was discussed and agreed at the first IWETG meeting on 16th May 2023. To note – the National Imaging Programme has recently identified a need to undertake a targeted piece of work looking at leadership and succession planning within organisations. The specific actions required and associated milestones are still under development however it is anticipated that this will feature within the 2023/24 workplan if resource to undertake this work can be secured. |  |
| Resources | Please outline any areas covered above that are dependent on resources not already confirmed: - A number of the strategy recommendations that are a priority area for 2023/24 require the establishment of distinct projects/ task and finish groups i.e., Advanced and Extended Practice, Leadership, and the creation of supplementary workforce plans for the wider imaging workforce. There is not capacity within the current programme team to undertake this work in its totality and the programme will be looking to recruit additional resources on a fixed term or secondment basis to take this work forward. - At the time of completing this document the HEIW review into Radiographer training and placement capacity in Wales has yet to be finalised. This report is due to be made available at the beginning of July 2023 and it is anticipated that there may be a number of recommendations which will need to be incorporated in the workplan of IWETG. |
| Interdependencies with other programmes | Please outline any critical interdependences with other programmes or organisations: - HEIW Education and Commissioning team input will be essential when reviewing the training and education requirements for registered and non-registered staff groups - HEIW Strategic Workforce Planning input/ support may be required in the delivery of a supplementary workforce planning event for Radiology Service Managers and in the production of supplementary workforce plans for the wider imaging workforce. HEIW Strategic Workforce Planning are represented on IWETG and are aware that this is detailed within the IWETG high-level programme plan. - IWETG is currently part way through participating in the Health Care Science Transformation Programme ESR Coding Review. Completion of this exercise and inclusion in subsequent phases of this work to develop workforce information dashboards will enable the programme to work towards the strategic aim of ‘ensuring services are able to access consistent reliable workforce information to enable effective workforce planning and facilitate the collection and monitoring of data on a local and national level’. |

Appendix 2b

Diagnostic Workforce Plan – Actions for 2023/24           	         Workforce Programme/Group covered:  National Endoscopy Programme

| Summary | Summary of key workforce priority areas for 2023/24 The key workforce priority areas for 2023/24 are aligned to the published National Endoscopy Programme Revised Action Plan, October 2022 which can be accessed via the Welsh Government website national-endoscopy-programme-revised-action-plan-october-2020_0.pdf (gov.wales). The Workforce, Training and Development Subgroup overarching aim is to support local workforce analysis, job planning, recruitment and retention and develop national training and development opportunities. The Workforce, Training and Development Subgroup is chaired by HEIW and is responsible for the governance of the delivery of the subgroup key actions outlined in the WG approved action plan. Whilst responsibility for the delivery of the Workforce actions sits within the NEP itself, the Endoscopy Training Management Group (ETMG) are responsible for the delivery of the agreed Training and Development actions. A summary for each key action be found below: Workforce Planning: - To ensure that all local endoscopy workforce plans are completed on an annual basis in a standardised template to enable effective regional and national endoscopy workforce planning and align with the IMTP process - To finalise, approve and publish the Endoscopy National Workforce Strategy in order to engage and consult with key stakeholders - To continue to validate and update the agreed national endoscopy workforce and training data set to ensure that annual submissions are in line with the aboveworkforce planning processes and that all data held on a national basis is captured in an accurate and timely manner - To develop best practice guidelines for job planning for individuals undertaking endoscopy sessions to ensure that productivity is maximised wherever possible - To continue to develop the Endoscopy Community of Practice and hold regular key stakeholder events is relation to building the future endoscopy workforce in Wales Workforce Standardisation - To ensure that all Health Boards adopt the national recommended Clinical Endoscopist job descriptions - Continue meetings of the Task and Finish Group created to look at supporting and developing the Clinical Endoscopist role (3 key themes: CPD, job planning, competency framework) - Roll out the standardisation of job descriptions across other professions within endoscopy - Maintain and continue to develop the endoscopy job description repository - Develop standardised scope of practice documents for registered and non-registered staff - Represent Wales on NHS England CE standardised Pay Project Recruitment and Retention - Repeat annual ‘PULSE’ survey on an annual basis to understand workforce challenges and opportunities and support retention initiatives - Develop retention best practice guidance alongside HEIW in response to PULSE survey - Analyse recent #BeVital campaign to understand success rate and work with HEIW to ensure sustainability - Support Health boards with local recruitment campaigns in relation to endoscopy - Continue to target key professions and areas via #BeVital attraction campaign - Task and Finish Group in place to look at specific endoscopy recruitment and retention challenges and develop local, regional and national solutions Training and Development - Develop the Endoscopy National Training Academy to support delivery of national, regional and local training in line with workforce demand, shape and supply - Ongoing identification of gaps and prioritisation of development in line with the 10 identified training pathways in line with competency frameworks, workforce and JAG requirements - Establish an approach to engaging and training a sustainable faculty supply and annual timetabling of training courses - Develop additional training for colonoscopists who have the ambition to become accredited screening colonoscopists - Roll out Administration and Booking Staff Band 3 UK Course across Wales - Develop a reliable training data repository for tracking learners - Create Education and training national/regional/local level infrastructure across Wales - Planned/available and sustainable training lists to support required number of “trainees” - Structured approaches to staff release and / or recruitment for participation in training programmes - Development of the central Endoscopy repository - HEIW Endoscopy Learning Pathways (HELP) structured around the ten training pathways, facilitating tracking of progress and acquisition of competences - Consistent approach to the use of Band 4 Assistant Practitioner in Endoscopy roles across Wales - Roll out ‘MEET’ tool (Maximising Efficiency Endoscopy Training) for list planning - Fast tracking training access for medical and surgical trainees to create independent endoscopists |
| --- | --- |
|  | Please outline the top 3 workforce risks that are impacting on access to or the quality of services (not HB specific) - Ageing consultant workforce, a high risk for those who deliver specialist endoscopy services (e.g. ERCP). A recent survey undertaken by the NEP shows that many are due to retire in the next 5 years with limited succession planning in place. - The number of workforce vacancies impacting upon the ability to deliver endoscopy sessions, particular challenges to recruit Gastroenterologists and Band 5 nursing staff in rural geographical locations (e.g. BCU and Hywel Dda) - Staff not being released for training and development due to the backlog of endoscopy lists which is impacting upon our ability to upskill our workforce. A recent PULSE survey undertaken by the NEP highlights this as having an impact upon the retention of nursing staff. |
| Specific workforce actions that will be taken forward in 2023/24 |  |
| Specific Actions & Milestones NEP Integrated Plan Update June 2023 |  |
| Resources | Please outline any areas covered above that are dependent on resources not already confirmed: - Access to improved workforce data at department level (current national database does not provide this) - Task and Finish Groups will require ongoing attendance and support from Health Board representatives to ensure they remain sustainable during and beyond the life of the programme - Increased reliance on Project Support staff to deliver key actions |
| Interdependencies with other programmes | Please outline any critical interdependences with other programmes or organisations: - HEIW to support the development of national workforce data set with level of granularity required to undertake workforce planning for endoscopy - HEIW Strategic Workforce Planning support and local Health Board WFP Leads to continue to develop local and regional workforce plans and submit on an annual basis in line with IMTP processes - NWSSP to provide recruitment activity reporting in relation to endoscopy vacancies and #BeVital campaign - NWSSP support to develop staff passports to enable movement of endoscopy workforce across existing Health Board boundaries - NWSSP support to develop endoscopy specialist staff bank - HEIW #TrainWorkLive to further develop and align #BeVital campaign to national approach to ensure sustainability |

Appendix 2c

Diagnostic Workforce Plan – Actions for 2023/24  	       Workforce Programme/Group covered:  National Pathology Programme

| Summary | Summary of key workforce priority areas for 2023/24 - Communication: Pathology training and NHS Wales Pathology careers and progression - Workforce: Recruitment, Retention, Capacity, Service Redesign, Culture & Leadership - Training & Education: Routes, Resources, Capacity, Research opportunities - Development of a National Pathology Academy and online learning platform - Development of a national pathology service operational workforce model |  |
| --- | --- | --- |
|  | Please outline the top 3 workforce risks that are impacting on access to or the quality of services (not HB specific) - Reduced workforce capacity in terms of workforce numbers and sickness absence is jeopardising service delivery and creating backlogs - Increases in service demand and complexity of testing – including to support adoption of new treatments and changes in clinical pathways (equity of healthcare provision) - Lack of protected time available for in-house staff for learning, including individual CPD – professional development, maintaining competencies and protected time for delivery of training |  |
| Specific workforce actions that will be taken forward in 2023/24 |  |  |
| Specific Actions: - Conduct a ‘Pilot’ of a Placement Education Facilitator (PEF) role in pathology - Establish a National Pathology Training & Education Co-ordinator role to develop a national pathology training and education model - Develop use of Advanced Practitioner role and training, to provide additional resources for cellular pathology dissection and reporting - Enable protected time for staff training and development - Develop costed options for a national Pathology training academy and online learning platform (building upon virtual platform that is available) - Improved communications of pathology training routes and careers in NHS Wales - Undertake a review of biomedical scientist training and education commissioning |  | Milestones: To be completed by Q2 2024/25 Model completed by Q2 2024/25 Ongoing Ongoing Online platform ongoing. Academy options to be completed Q1 2024/25 Ongoing – to be completed by Q4 2023/24 To be completed by Q1 2024/25 |
| Resources | Please outline any areas covered above that are dependent on resources not already confirmed: PEF not confirmed Continued support from the pathology service to the Programme |  |
| Interdependencies with other programmes | Please outline any critical interdependences with other programmes or organisations: Welsh Government HEIW & Healthcare Science Programme Health boards/trusts IBMSIBMS (Institute of Biomedical Science) |  |

Appendix 2d

Diagnostic Workforce Plan – Actions for 2023/24  Workforce                                                        Programme/Group covered:  Genomics

| Summary | The Genomics Delivery Plan for Wales was published by Welsh Government (December 2022) and requires the development of a Strategic Workforce Plan to be led by HEIW working with Genomics Partnership Wales (GPW). The Genomics Delivery Plan is aligned with the UK ten-year strategy Genome UK: The Future of Healthcare. Genomic medicine is an area of rapid advancement and there are already significant developments in this field that are impacting on the delivery of services and care to patients. There are workforce challenges to be addressed and a need to increase the pipeline of people in the specialist workforce including bioinformaticians, genetic counsellors, clinical scientists and genetic technologists in various areas of genomic medicine including microbiology and molecular pathology, and clinical geneticists. There is a need to develop and fully embed education and training programmes for our non-specialist workforce including people who need a basic understanding of genomics as well as those who will require dedicated and expert knowledge to respond to changes in clinical and service pathways. Surveys have found that the majority of the workforce is poorly informed about genomics and do not recognise its importance and/or relevance. The plan should include actions to provide new training packages; identifying dedicated education and training officers; establishing a network of genomics quality leads; ensuring there are national genomics leads for core specialties that align with workforce plans in relevant areas (such as oncology and pharmacy); supporting staff to be competent in consent-taking and interpreting results; considering the development of clinical research and its impact on the delivery of patient care in the future. Importantly the plan should align with and maximise the opportunity of UK shared commitments through collaboration with the Genomics Training Academy. |  |
| --- | --- | --- |
|  | Please outline the top 3 workforce risks that are impacting on access to or the quality of services (not HB specific) - Lack of specialist expertise and knowledge (non-clinical) such as bioinformaticians and laboratory workforce - Lack of specialist expertise and knowledge (clinical) such as genomic medicine workforce. - Lack of basic understanding in non-specialist (clinical) workforce. |  |
| Specific workforce actions that will be taken forward in 2023/24 |  |  |
| Milestone 1: - HEIW to draft an initial scope and approach to development of workforce plan with Genomics Partnership Wales including a timetable for development. - HEIW to undertake a review of relevant UK Strategies that will help to inform development of the plan. - Roll out an initial offer of education for the workforce via an e-learning package and the availability Level 7 modules. Milestone 2: - Secure agreement on the scope of the plan following established governance route, i.e. GPW Board approval with sign off via the National Diagnostics Programme Board. - HEIW to complete Strategy mapping to provide a high-level assessment of the key issues and direction of travel. - Scope specific requirements in respect of pharmacogenomics. Milestone 3: - Start engagement with stakeholders on the key actions following strategy mapping and data analysis. - Scope models of potential enhancements to education and training infrastructure (i.e. local and national specialty leads) incorporating learning from other UK nations. Milestone 4: - Conclude engagement phase. - Develop initial set of actions for testing with stakeholders at the start of 2024/25 and to inform development of the HEIW Education and Training plan submission in July 2024. |  | Actions: - HEIW to develop a communications plan to roll out e- learning and publicise modular genomics education programme. - HEIW & GPW to draft scope of workforce plan following established governance route i.e. GPW Board approval with sign off via Diagnostics Programme Board. - Start initial strategy mapping. - Fully launch the master’s level modules in Genomics. - Develop MOU (or similar) with HEE/NES to access resources already developed (e.g. GE Notes). - Arrange workshop(s) to support scoping of the plan. - Build relationships across the UK genomics education and training architecture. - Map existing data sources to gain an overview /understanding of current specialist workforce. - Scope actions in respect of Advanced Therapy Medicinal Products (ATMP). - Engage with other UK nations on models. - Procure support from specialist partner on engagement phase including expertise to help with developing an initial set of actions. - HEIW to develop a stakeholder engagement plan - Run engagement phase during Q4 with web surveys, stakeholder discussions and other engagement events led by specialist partner. - HEIW/GPW to deliver formal report to National Diagnostics Programme Board. |
| Resources | Please outline any areas covered above that are dependent on resources not already confirmed: N/A |  |
| Interdependencies with other programmes | Please outline any critical interdependences with other programmes or organisations: HEIW, GPW, WG, NHS, HEIs, AWMGS, Wales Gene Park, PHW/Pathogen Genomics Unit/Public Health Genomics Programme, patient and public representation (through GPW Patient and Public Sounding Board), Health Boards, other UK nations. Also other programmes – National Pathology and Imaging programmes, Healthcare Science Programme (through National Diagnostics Board), and Advanced Therapies Wales (ATMPs) |  |

Appendix 2e

Diagnostic Workforce Plan – Actions for 2023/24  Workforce                                       Programme/Group covered:  Healthcare Science

| Summary | HEIW includes an objective in its IMTP to “Effectively manage the Healthcare Science Programme to implement the future vision for the healthcare science workforce described in the national framework.” The Healthcare Science Framework, published in 2018, sets out the vision for healthcare science as a profession. This profession covers the majority of services in the NHS, and therefore the programme is delivered with predominantly a profession-focus, rather than a service-focus, working across the breadth of HEIW and with the many service-focussed programmes to meet its aims. Working across HEIW, activity to develop the profession in 2023-24 is focussing on improving the workforce data quality, expanding opportunities for learning, research and innovation, promoting registration and continuing to raise the profile of the profession as a whole. Outcomes from this work, and incorporating work across HEIW deliverables for healthcare science, seek to achieve: - A clear intelligence position of our current workforce - Strengthened accessible healthcare science careers, with improved recruitment and retention through a quality approach and promotion of accreditation - Research and innovation enabled across all healthcare science services to improve evidenced based diagnostics for patient care throughout the NHS - A strong collaborating collective professional voice understood and valued throughout the system |  |
| --- | --- | --- |
|  | Please outline the top 3 workforce risks that are impacting on access to or the quality of services (not HB specific) As described above, this programme focusses on professions across Healthcare Science, rather than services. As such, the following workforce risks are noted: - Lack of training and development capacity – with training models based upon historic levels of capacity, we are now seeing challenges to placement uptake and reductions in IMTP requests for training in the profession - Loss of both newly trained and experienced healthcare scientists to NHS England and private sector/industry - Lack of awareness/inclusion of valuable healthcare scientist roles, such as those of Medical Physicists, Clinical Engineers, Clinical Photographers, Physiologists and Bioinformaticians, within diagnostics transformations |  |
| Specific workforce actions that will be taken forward in 2023/24 |  |  |
| Specific milestones described within the HEIW IMTP Objective for Healthcare Science: Milestones for Quarter 1: - Finalise changes to workforce coding to improve workforce data for healthcare scientists and supporting workforce. - Scope requirements for widened learning opportunities (travel fellowship programme) including international opportunities. Milestones for Quarter 2: - Baseline the current innovation capability and capacity of healthcare scientists. - Facilitate mechanisms for collaboration across the profession to increase service accreditation levels. Milestones for Quarter 3: - Roll out NHS Wales wide changes to workforce data guidance for healthcare science. - Co-produce a proposal of preceptorship for the profession that maximises opportunities and seeks to meet the needs of the newly registered professional, undertake consultation, and seek approval of stakeholders. Milestones for Quarter 4: - Finalise and publish strategic plans to increase innovation capability and capacity, to deliver preceptorship of healthcare scientists and to enable access or improvements to service accreditation for identified services. - Launch the travel fellowships programme for healthcare scientists. |  | Additional (abbreviated) objectives across the breadth of HEIW’s 23/24 IMTP, supported by Healthcare Science Programme with reference to Diagnostics: - Develop a comprehensive Education and Training Investment Plan - Implement an improvement programme for clinical placements - Implement strategic review phase 2 priorities including the redesign and re-procurement of post registration education programmes. - Identify the priority areas for the first phase of the Work Based Learning element of Y Ty Dysgu - Ensure effective implementation of the pre-registration contracts - Develop a multidisciplinary education strategy setting the future vision and principles to guide our work to transform education. - Complete roll out of multi-professional quality framework for education and training to ensure continuous improvement - Implement the multi-professional strategy for Simulation-Based Education and Training. - Fully implement and evaluate the ‘Y Ty Dysgu’ learning management system to improve workforce learning. - Progress the development of a Strategic Workforce Plan for Genomics - Continue to prioritise the implementation stages of the Workforce Strategy and communicate plans with partners and stakeholders. - Establish a workforce observatory function to support horizon scanning, scenario planning, modelling and strategic workforce planning in NHS Wales - Develop and improve the data intelligence function to inform work in HEIW and working with partners, improve the governance, quality and standards of workforce data across NHS Wales. - Implement an agreed programme of careers and outreach activity, incl. development of Careersville to broaden its reach to all-ages. - Implement actions to support recovery in relation to planned care and recovery including diagnostics and cancer national programme - Lead the implementation of the assurance framework for multi-professional Advanced Practice (AP) and Consultant Practice. - Implement priority actions from the Critical Care Workforce Review - Create the career progression framework for the support workforce - Support the implementation of a multi-professional CPD strategy - Implement the national digital capability framework for the healthcare workforce (for those who are not digital professionals) - Implement a cohesive communication, engagement and promotional plan to increase awareness of Gwella@HEIW - Market, recruit and deliver the Advanced Clinical Leadership Programme and Clinical Leadership Fellowships Programme - Co-produce and deliver a quality assured national Compassionate Leadership development programme - Market and recruit to Executive Director Talent Pools in support of senior leader succession planning and develop national resources to support the induction and onboarding into NHS Wales - Enhance Gwella@HEIW with talent management software - Review and update with partners the NHS Core Principles - Advance equality in training and education for students, trainees and learners undertaking training commissioned/provided by HEIW - Deliver the required actions in More Than Just Words to increase the Welsh language skills of the workforce |
| Resources | Please outline any areas covered above that are dependent on resources not already confirmed: N/A - The Healthcare Science Programme is funded to deliver this work, with both staffing and programme budget. |  |
| Interdependencies with other programmes | Please outline any critical interdependences with other programmes or organisations: Directors of Therapies and Health Science Welsh Government Health Science Policy team NHS Executive national programmes and networks, which provide the service-focussed responsibilities in the areas that they represent (Pathology, Imaging i.e. Diagnostic Radiography, Genomics, AMTP, AWMOL, PET, Primary Care, Planned Care, Respiratory Network, Neurological Conditions Network) Welsh Scientific Advisory Committee and its subcommittees – particularly Medical Physics, Clinical Engineering, Clinical Physiologies where there are no national service-focussed programmes funded National School for Healthcare Science Chief Scientific Offices in England and Scotland |  |

Appendix 3

Diagnostics: Extracts from IMTPs 2023/24

| Aneurin Bevan | As of January 2023, the number of people waiting over 8 weeks for diagnostics was 2,599 with significant improvements seen in Cardiology, driven by use of an insourcing company to provide echocardiogram capacity. Demand for endoscopy has increased by 18% compared with pre-Covid rates, however, waiting times have reduced by 13% through insourcing additional capacity. An in-house endoscopy unit at RGH site will open in 2023 and recruitment to support additional capacity is ongoing. Imaging has seen a sustained increase in demand for CT scans (8% higher than pre-Covid) and MRI scans (15%). This trend is expected to continue over the life of this plan The outcome of the Regional Diagnostic Centre work will have a material impact on the nature and range of solutions that will be progressed within the Health Board as opposed to wider solutions that address diagnostic capacity shortfalls across South East Wales. Our pathology services, like those in many NHS organisations across Wales are under substantial pressure due to workforce challenges; inadequate estates/facilities, inadequate digital infrastructure, increasing demands on pathology services due to post Covid-19 recovery and the detrimental effect that insufficient capacity in the current system is having on patient waiting time and diagnosis. Diagnostics are an essential component of nearly all patient pathways and provide the evidence base upon which all clinical decisions are made. Diagnostic capacity was already stretched before the pandemic and these pre-existing service frailties, particularly in respect of radiology reporting, endoscopy capacity, cellular pathology, neurophysiology and cardiac physiology diagnostics have been acutely exacerbated as a consequence of Covid-19. Our diagnostic services continue to increase capacity for all patients, however, the backlog in patients needing to be seen and consequently requiring diagnostics is putting pressure on services. We have continued insourcing additional endoscopy capacity, and this has enabled us to maintain the 8-week backlog. The future development of the endoscopy unit at RGH has progressed with approval to recruit ahead of the new unit opening in 2023. We also insourced echo capacity resulting in a substantial reduction in the numbers waiting for echocardiograms. Histopathology demand and backlog are expected to be maintained at current levels of pressure. Radiology diagnostics continue to experience an increasing trend in demand for CT (weekly average 1300 to 1400) and MRI (weekly average 620 to 695) and anticipate this will continue over the coming year. Community Diagnostic Hubs In September 2022 the Chief Executives across CAVUHB, CTMUHB and ABUHB collectively supported the principle of progressing a series of regional diagnostic solutions through the implementation of Community Diagnostic Hubs (CDH) across South East Wales. There is clinical consensus that any service development undertaken regionally must meet the following key criteria: - Delivery is more accessible to residents living in areas of deprivation and able to deliver to more than one health board population in the region - Developments deliver an increase in capacity - Developments will be founded on seeking sustainable solutions to demand backlogs. A service specification is under development is for the procurement of a number of CDHs with the strategic ambition to have the first CDH ‘live’ during Quarter 2 2023/24. The health board currently considers that considerable work is required to ensure delivery of a cost- effective option in a regional context that provides accessible services consistent with local requirements and priorities. It is acknowledged that provision of a hub delivering MR, CT, plain film and ultrasound services through a managed service contract will require a seven-year commitment with a total cost in excess of £18M. The funding proposals to support rollout for such a programme are currently uncertain, and it is therefore not possible to make a commitment in respect of the coming financial year. Colleagues within Cwm Taf Morgannwg UHB are undertaking feasibility studies regarding the ‘Concorde’ site in Llantrisant, which has been purchased with a view to support and facilitate additional regional service capacity as / where clinically and practically appropriate. It is currently considered impractical for this site to form a managed service CDH option for ABUHB residents due to issues of accessibility, cost, clinical governance, informatics support, public engagement, deliverability and exit strategy. The priority for the health board in 2023/24 will therefore be to progress plans for a local CDH consistent with the strategic vision, utilising an existing site and in-house delivery / provision. We are well-placed locally to deliver a cost-effective model, with separate existing inpatient / outpatient pathways, manageable recruitment and a relatively strong baseline waiting list position. Specific tasks for the year will include the following: - - Submit business justification case for a second MRI scanner within the Grange University Hospital, providing dual benefits of increased service resilience on the site and the ability to free up capacity on other sites. - Utilise released capacity as the basis for a CDH development at Ysbyty Ystrad Fawr in the Rhymney Valley, potentially supplemented by additional CT / ultrasound capacity - Develop revenue and capital business cases / implementation plans for the CDH linked to the above, based on in-house provision and delivery, with funding sought through the regional diagnostic board arrangements and governance mechanisms. It is envisaged that an in-house CDH solution based on an existing local general hospital site will provide the required accessibility and deliver savings of over £5M compared to managed service contract agreements for a similar capacity. |
| --- | --- |
| Cardiff and Vale | Diagnostics and Therapies key area of focus - Maximise productivity of all diagnostic disciplines - Working within regional context, progress the development of the community diagnostic hub - Progress planning and commissioning of two new Endoscopy suites in UHL - Continue to reduce waiting times and innovate delivery of inpatient and outpatient therapies - Continue our engagement in the national development of clinical information systems including LINC and RISP. Pathology A Regional Pathology Steering Group has been established recognising the fragility of current pathology services due to workforce challenges; inadequate estates/facilities, inadequate digital infrastructure, increasing demands on pathology services due to post Covid-19 recovery and the detrimental effect that insufficient capacity in the current system is having on patient waiting time and diagnosis. The project has been created to oversee the identification, development and implementation of regional pathology solutions in South East Wales to create a robust, sustainable, future proofed and patient focussed service. All pathology disciplines will be included in this work however it was recognised and reinforced at the planning conference that in the first instance the focus will be on Cellular Pathology. Strategic commissioning intentions – increase community diagnostics and point of care testing Community Diagnostic Hubs In September 2022 the Chief Executives across CAVUHB, CTMUHB and ABUHB collectively supported the principle of progressing a series of regional diagnostic solutions through the implementation of Community Diagnostic Hubs (CDH) across South East Wales. There is clinical consensus any service development undertaken regionally must meet the following key criteria: - Delivery is more accessible to residents living in areas of deprivation and able to deliver to more than one health board population in the region - Developments deliver an increase in capacity - Developments will be founded on seeking sustainable solutions to demand backlogs. A service specification is under development is for the procurement of a number of CDHs with the strategic ambition exists to have the first CDH ‘live’ during Quarter 4 2023/24. The Diagnostic programme is currently undertaking feasibility studies regarding the Llantrisant Health Park to consider if this site is a suitable for location for a Community Diagnostic Hub. The priority for the health board in 2023/24 will be to also ensure plans are also progressed through the Diagnostic programme for a further CDH which in addition to the above will also be available to the Cardiff and Vale population. This is consistent with the strategic vision |
| Cwm Taf Morgannwg | Regional Diagnostic and Treatment Centre for South East Wales A key strategic development for the South East Wales region during 2022 was the purchase of an estate adjacent to the Royal Glamorgan Hospital, supported by Welsh Government capital funds, which is intended to allow for the development of a Regional Diagnostic and Treatment Centre. This presents significant opportunity to transform services on a regional footprint to deliver improved access to elective diagnostic assessment and treatment for the patients in the South East region. Radiology Our short-term objective is to improve waiting times for our patients to deliver access within 10 days for suspected cancer referrals, under 4 weeks for urgent referrals, and return to achieving the under 8 weeks target for routine referrals to assist recovery plans. We will achieve this through: - Demand and capacity assessment and process mapping to drive efficiencies with developments including continued rollout of electronic requesting and implementing electronic vetting to deliver faster receipt of referrals, clearer information and improve overall patient waits. - Development of the out of hours radiology services. - Redevelopment of radiology services in Prince Charles Hospital is expected to deliver improvements in patient flow and much improved environments for staff and patients. - Diagnostics is a priority area for development within the planned care recovery programme and the health board is working with partners to develop regional capacity. Pathology The Pathology service comprises four sub specialities that are fundamental to diagnostic pathways, and the flow of patients through our health services across primary, secondary and tertiary care. These are Cellular Pathology, Clinical and Laboratory Haematology, Biochemistry and Microbiology. During 2023-24 we will: - Provide a FIT (colorectal cancer screening) service in conjunction with Gastroenterology and primary care teams to ensure access to further diagnostics for symptomatic patients. - Deliver INR self-testing for patients using anti-coagulants, in collaboration with primary care. - Develop the pathology estate to ensure it is able to deliver an efficient and effective service. - Work with Swansea Bay University Health Board to confirm the future of pathology services for the Bridgend population. - Implement digital pathology approaches including the use of artificial intelligence across all areas of Pathology. This includes the national laboratory information management system. - Develop and implement our three-year workforce plan, in liaison with regional and national partners and developments, to ensure we are able to provide a sustainable workforce and reduce reliance on locum staff. - Work with Health Board partners to develop regional pathology services, with an initial focus on cellular pathology A Regional Pathology Steering Group has been established recognising the fragility of current pathology services due to workforce challenges; inadequate estates/facilities, inadequate digital infrastructure, increasing demands on pathology services due to post Covid-19 recovery and the detrimental effect that insufficient capacity in the current system is having on patient waiting time and diagnosis. The project has been created to oversee the identification, development and implementation of regional pathology solutions in South East Wales to create a robust, sustainable, future proofed and patient focussed service. All pathology disciplines will be included in this work however it was recognised and reinforced at the planning conference that in the first instance the focus will be on Cellular Pathology. It is accepted that a comprehensive digital cellular pathology system is a pre-requisite for meaningful regional service collaboration and integration, and this should therefore be the key work stream for progress in 2023/24. In support and anticipation of this, Health Boards will review workforce plans and areas of potential advance collaboration e.g. training and accreditation to ensure that services are in a position to progress on a timely basis later in the year. Essential continuity and recovery plans will also be progressed at each local level. Community Diagnostic Centres In September 2022 the Chief Executives across CAVUHB, CTMUHB and ABUHB collectively supported the principle of progressing regional diagnostic solutions through the implementation of community diagnostic centres (CDC) across South East Wales. There is clinical consensus any service development undertaken regionally must meet the following key criteria: - Delivery is more accessible to residents living in areas of deprivation and able to deliver to more than one health board population in the region - Developments deliver an increase in capacity - Developments will be founded on seeking sustainable solutions to demand backlogs. This project will source NHS-based options where feasible and alongside this, a service specification is under development is for the procurement of a number of CDCs to be situated throughout the region to ensure accessibility, with the strategic ambition to have the first CDC ‘live’ during Quarter 4 2023-24. Feasibility studies will be undertaken for site selection, and this includes feasibility assessment of the Llantrisant Health Park to consider if this site is a suitable for location for a Community Diagnostic Centre. The Health Board has committed to investment in CDC development for 2023-24. National Imaging Academy CTM is host to the National Imaging Academy Wales. There are two lead executives who directly support this function (Lauren Edwards and Linda Prosser). The hosting agreement has been refreshed and extended for a further 3 years. Thus the health board, through working closely in support of the NIAW Director and via its business meeting continues to have a pivotal role to play in supporting the required increase in the diagnostic workforce, including considering new roles and ways of working. |
| Hywel Dda | Regional Diagnostics Plan Diagnostic Context and Challenges, and Regional Solutions Diagnostic interventions are an integral aspect across all specialities and medical areas the importance of timely diagnostics across all pathways is fundamental to achieving the Urgent Suspect Cancer and Referral to Treatment ministerial priorities. However, there is significant fragility at present within a number of key diagnostic interventions where demand and capacity do not align. Equally, there is a significant reliance on an external party to read the scans and support the Out of Hours rota: Endoscopy is extremely challenged across all modalities, with circa 75% of patients routinely waiting over 8 weeks for Colonoscopies, Cystoscopy, Flexible Sigmoidoscopy and Gastroscopies Cardiology is extremely challenged within both Echocardiograms and CT angiography Echocardiograms have circa 67 routinely waiting in excess of 8 weeks across the Health Board. Bronglais is the site impacted the most with 83 of patients waiting in excess of 8 weeks. In order, to address these waits the service continues to have a robust triage system in place, attempt to source locums and will utilise the demand and capacity work that is currently being undertaken. The service has also commenced an insourcing solution and the intention is that this will run into 2023 24 at greater capacity. In house staff are also being offered enhanced payment rates to increase activity. There is also a medium to longer potential option to “grow our own” capacity by securing additional workforce, which is currently going through a Value Based Healthcare approach. The only substantive CT Coronary Angiography capacity within the Health Board is at Bronglais which provides a capacity of approximately 150 per year. The Health Board also commissions this from Swansea Bay. An additional list has run at Glangwili since August 2022 but with short term project funding which will cease in July 2023 this is currently undergoing a Value Based Healthcare approach with business case for sustainability due in May 2023. CT Coronary Angiography demand for Hywel Dda is approximately 600 800 per year. With a current substantive capacity of 150 at Bronglais and the capacity at Swansea Bay UHB, the development of substantive capacity at Glangwili and future further capacity at Withybush and Prince Philip Hospital are priorities for the service in the coming 12 18 months. Additionally, 5 Cardiologist underwent training in CT Coronary Angiography in 2022 which now provides a skill capacity of 7 Cardiologists spread across all 4 acute sites. Non Cardiac Computed Tomography Performance relating to GP and Consultant referrals across all 4 sites for non cardiac CT is very good at 90%> of patients being seen in 8 weeks or less. However, the model relies heavily on an external provider which comes at a significant expense. Therefore, the model is not sustainable and does not have the productivity level (despite the good performance) of a substantive workforce model (as the provider needs to discuss 20% of cases with University Health Board staff) Non Cardiac Magnetic Resonance Imaging (MRI) performance is extremely challenging with less than 59% of patients (GP referrals) having their MRI within 8 weeks (at a University Health Board aggregate level). The majority of the 8 weeks > waits are within Prince Philip, where only 30% of patients are waiting < 8 weeks. MRI (Non Cardiac) performance is slightly higher within Consultant referrals with 61% of patients currently under 8 weeks. Non Obstetric Ultrasound performance for Consultant referrals remains around 81% (aggregated) for patients waiting 8 weeks or less. The performance for GP referrals is higher across Glangwili, Bronglais and Withybush General Hospitals achieving circa 88% (aggregated across the three). However, the number of patients waiting 8 weeks or less in Prince Philp Hospital is 65%. Regional Diagnostic Hubs During 2023/24, we will develop a Business Plan for both Health Boards Executive Boards’ agreement outlining any potential financial ask and next steps. This will include any requests for funding that could be sought for regionally led and managed programme resource for programme delivery from central funding. However, work has already begun on both our regional pathology centre of excellence, and on regional endoscopy. Planning objective: Develop and deliver a regional diagnostic plan with Swansea Bay University Health Board by Spring 2024. Planning objective: Implement the planned care recovery programme in compliance with Ministerial priorities. Specific deliverables: Radiology Scanning (CT/MR/Plain film) - Continue to utilise locum Radiographers to fill gaps in areas of staffing vacancy and where staffing is under resourced until new graduate appointments are on board, inducted and established Utilise findings of capacity and demand work currently being undertaken - Utilise the D&C work to inform and implement a sustainable solution to extend the working day to reduce pressure and reliance on overtime and agency work. At present, we utilise Ever light for a significant reporting of OOH scans. A sustainable model can reduce the reliance on Ever Light, whilst ensuring the current CT capacity is not only maintainable, but the productivity can be increased by circa 20-25% - Recruitment of 12 radiographers, lead in time for training However, once complete will be fast tracked into areas most needed, which will free up capacity for the more experienced radiographers (the benefits of the 12 additional radiographers are more likely to be end of year 2 / beginning of year 3) Radiology Reporting (CT/MR/Plain film) - Continue to outsource the reporting element where internal capacity and insourcing options cannot meet demand Utilise the findings of capacity and demand work currently being undertaken to realise the staffing resource required to enable the implementation of a sustainable solution to meet demand which would include options such as extending the working day to reduce pressure and reliance on outsourcing - CT Out of Hours look at rotas, potential option to bring in a locum Radiologist overnight - Plain film - recruited a readily trained reporter - Recruitment of 2 part time radiologists to replace impending retirement roles, in order to meet demand. Allow Consultants to work more flexibly to attract work force and maintain work life balance DXA - Expand Bronglais service to be able to provide full clinical reports in line with those provided by Swansea Bay UHB, option to upskill existing staff with potential support from Swansea Bay UHB - Procurement of a new DXA scanning machine at Bronglais General Hospital, through the potential of charitable funds Key challenge is 7 Day turnaround for diagnostics for all tumour sites Programmes of work planned for 2023/24 - Regional Pathology Centre of Excellence including Cellular Pathology, Microbiology, Genomics, Laboratory Medicine, Digital - Diagnostic Hubs, with the work programme being defined to include Endoscopy, Radiology, Orthopaedics, and Neurology - Cardiology including improving the provision Cardiac Computed Tomography (CT) training; Echo/Cardiac Physiology extending working hours and building a resilient workforce; Cardiac Pacing Repatriation of Hywel Dda patients; Cardiac Magnetic Resonance imaging (MR) service developments and improving the provision - Neurosciences including an epilepsy business plan; neurophysiology; and neuromuscular disorders |
| Powys | The equivalent of 1 in 5 of the population of Powys are on a waiting list for planned care, including diagnostics, in or out of county. There are national workforce shortages and fragility of in reach, with increases in breaches for 8 week waits for diagnostics in the specialities of non-obstetric ultrasound and musculoskeletal health. Actions to recover include waiting list reviews, sonographer training and joint work on capacity with providers. As part of the Accelerated Sustainable Model, a renewed approach to diagnostics for Powys residents has the potential to radically transform patient pathways improving outcomes for conditions such as cancer, stroke, heart disease, respiratory disease, dementia and many more – as well as increasing access closer to home. Driving forward the transformation of diagnostics will be a key part of the work on the Accelerated Sustainable Model. The Powys model is “whole system” and is aimed at improving outcomes, experience and cost through earlier detection of conditions at more treatable stages. It starts with self-awareness of wellbeing and prevention and includes close attention to inequalities. It spans people in their own home, through to health boards working together to secure regional and specialised solutions. As a large rural border region collaboration is key and the health board intends to form stronger strategic partnerships to help build more sustainable pathways of care. The Diagnostic Strategic Intent sets out the overarching direction. Implementation will be phased and incremental over the next three years, taken forward through separate business. Key drivers are: - Effectiveness in terms of improved outcomes and value - Empowerment of patients and professionals, so there is well informed shared decision making - Efficiency including addressing backlogs due to Covid-19 and adopting new ways of working - Environmental (reduced patient and transport journeys) - Emerging technologies and learning from innovation including responses during the pandemic PTHB has been able to drive forward initial work on transformation: the Strategic Intent has been developed. Testing was rolled out across primary care; the first phase of the community cardiology service was successfully established; work to implement Transnasal Endoscopy was initiated; access to Rapid Diagnostic Centres was taken forward in collaboration with other health boards and NHS Trusts; continued developments in respiratory diagnostics were taken forward including spirometry, the repatriation of sleep studies and lung function testing; and cases to take forward the next phases of work in 2023/4 onwards were agreed including dermatology in primary care; the next phases of community cardiology; and in relation to dermatology diagnostics in primary care. The Discovery phase of the Accelerated Sustainable Model highlighted key findings in relation to health service use by the Powys population (and associated resource allocation). As well as improved clinical patient and clinical outcomes, efficiency gains should be delivered for example avoidance of duplication of imaging through IT networking, networking of pathology tests and reductions in acute admissions and length of stay. This includes expansion of diagnostics provision outside district general hospitals including imaging such as scanning and x-ray, tests and monitoring for cardiac and respiratory functions, pathology, phlebotomy and endoscopy. As part of the Accelerated Sustainable Model, building on the work to date, over the next three years Powys will take forward the phased implementation of the Diagnostic Strategic Intent supported by specific business cases. All three Powys Clusters have identified diagnostics as a priority, supporting the design of in county services, including cardiology, dermatology, musculoskeletal conditions, with a focus on immediacy of access to diagnostic results. |
| Public Health Wales | By 2026, working closely with our partners, we will have an agreed service model that includes new diagnostic and treatment capabilities for infectious diseases and has the capacity and skills to introduce and embed innovation. Our microbiology services will continue to provide world class diagnostic and clinical advisory services and Specialist and Reference Microbiology Services to support diagnostics, surveillance, and outbreak identification and management |
| Swansea Bay | Planned care goals and methods: Increase cardiac, respiratory and neurophysiology diagnostic, capacity including direct access for primary care. Expand dual energy X ray absorptiometry (DEXA) capacity across the south west Region. Increase core capacity in radiology through a combination of additional machine and reporting capacity and working regional with Hywel Dda to identify opportunities for mutual support. Roll out of Primary Care Audiology Programme which includes First Contact Advanced Audiologists providing hearing and tinnitus assessment and advice. Combined with routine and complex wax removal. Continued development of associate audiologist pathway and to reduce Ear Nose Throat outpatient referrals. Diagnostic Hubs, with the work programme being defined to include Endoscopy, Radiology, Pathology, Orthopaedics, and Neurology A joint commissioning agreement with HDUHB for Regional Pathology Services which will optimise use of our joint resources and highly skilled workforce to deliver high quality services for the region Cardiology including improving the provision Cardiac Computed Tomography (CT) training; Echo/Cardiac Physiology extending working hours and building a resilient workforce; Cardiac Pacing; Repatriation of Hywel Dda patients; Cardiac Magnetic Resonance imaging (MR) service developments and improving the provision Neurosciences including an epilepsy business plan; neurophysiology; and neuromuscular disorders |
| Velindre | Support the development of the diagnostic network and single cancer pathway as key enablers of service transformation. Our capacity challenge will not only be in the delivery of treatment by SACT and radiotherapy, but also in the other services which support patient care including radiology, therapies, pharmacy and palliative care. 9% forecast growth in demand for Radiology Imaging in 2023/24 |

Appendix 4

Strategy Mapping – Diagnostic Workforce Plan The documents noted below have been reviewed to identify the key themes and issues relating to the diagnostic workforce to inform a set of actions to be taken forward over 2023-205. Please note: This table is not an exhaustive list and does not include a review of the literature in its entirety. Nor does it include a detailed review of all profession specific materials Version 0.7 November 2023

| Overarching Strategy and Policy Documents |  |  |  |
| --- | --- | --- | --- |
| Ref | Key document | Key reference points, actions and priorities for diagnostic workforce planning | Relevance to workforce plan |
| 1. | A Healthier Wales (2018) A healthier Wales: long term plan for health and social care ¦ GOV.WALES | This plan sets out a long-term future vision of a whole system approach to health and social care, building on the philosophy of prudent healthcare. In order to achieve this, new models of seamless local health and social care will be built on a local and national basis. These models will build on a foundation of local innovation including through Clusters of primary and community care providers. Aims of strategy: - Longer, healthier and happy lives - A whole system approach to health and social care - An equitable system which achieves equal health outcomes for all - Services which are seamless and delivered as close to home as possible - People will only go to a general hospital when it is essential - Using technology to support high quality, sustainable services | Shift in emphasis towards a ‘closer to home’ approach to the delivery of care which is set out in subsequent publications relevant to diagnostics. Emphasis on technological advances to improve access and experience for patients in accessing care. |
| 2. | Our programme for transforming and modernising planned care and reducing waiting lists in Wales (2022) Our programme for transforming and modernising planned care in Wales and reducing the waiting lists (gov.wales) | The Programme highlights the need to prioritise Diagnostic services recognising them as an essential component of nearly all pathways but an area which is not currently able to meet demand so building capacity and expanding the diagnostic workforce is critical in this. Have committed to spending £262m annually to equip and train the next generation of health workers but notes that simply continuing to grow the existing workforce will not be enough and we will need to find ways to release additional capacity and work in different ways i.e. advocating a delivery model that supports professionals to work at the top of their licence. Need to streamline the diagnostic part of the pathway to drive efficiency and access through revising working arrangements to deliver ambition for extended hours across 7 days to support hot reporting which is essential. This will require a flexible approach to job planning. |  |
| 3. | Diagnostic Recovery and Transformation Strategy for Wales (2023) Diagnostic Recovery Transformation Plan for Wales (gov.wales) | This Welsh Government Strategy for NHS Wales sets out the priorities for Diagnostics over 2023-2025 with nine themes of focus. Whilst there is a specific workforce theme with the following actions: - Significantly increase the training pipeline of diagnostic specialists including advanced practitioner roles (e.g. reporting biomedical scientists, reporting radiographers, advanced audiology primary care practitioners) and consultant grade roles (e.g. consultant clinical scientists) as part of the service redesign. - Adopt the Imaging Academy model for other disciplines to support training and development of the diagnostic workforce. - Continue to develop prudent multi-professional working for diagnostics - Actively pursue hybrid working and ‘reporting from home’ The requirement for workforce to enable the other areas of focus i.e. Service Transformation, Digital, Commissioning is implicit and not all directly requiring a diagnostic capability but skills within these individual areas. |  |
| 4. | Diagnostics: Recovery and Renewal (“Richards” review) 2020 NHS England » Diagnostics: Recovery and Renewal – Report of the Independent Review of Diagnostic Services for NHS England | This independent review was commissioned by NHS England and although it has no formal status in Wales, the recommendations are applicable. From a workforce perspective, the Richards review highlighted the need to rapidly increase the workforce to support the growing demand for diagnostic services. The specific workforce recommendations are set out below: - Expand the imaging workforce through increases in training pipeline and assistant practitioner and support roles - Increase the number of advanced practitioner radiographer roles and assistant practitioner roles - Establish Training Academies for endoscopy to expand colonoscopy with associated increase in specialist practitioners and endoscopy nurses - Increase the number of echocardiographers and clinical scientists - Expand the pathology workforce, specifically histopathologists, advanced practitioners and health care scientists with a focus on skill mix - Develop of genomic scientist roles and medics in line with national genomic planning - Support organisations to work together to deliver changes in diagnostics workforce particular in driving skill mix initiatives across the country. For context, the report estimated that there was likely to be a shortfall in key roles in England over 5 years of around 11,000 roles, which would equate to circa 650 roles in Wales. It should be noted that these estimates were calculated pre-pandemic and given the post-Covid backlogs, this is likely to be an underestimate of the position. |  |
| 5. | Aligned to Richards Review: NHS England GiRFT Diagnostics Delivery Guide- A guide for systems in delivering effective diagnostic services to support Elective Recovery -November 2022 Diagnostics-guide-to-support-elective-rexcovery-Nov-2022.pdf (gettingitrightfirsttime.co.uk) With references to: Radiology GIRFT Programme National Specialty Report-Nov 2020 Layout 1 (gettingitrightfirsttime.co.uk) The GIRFT Pathology national specialty report was published in Nov 2021, with almost all its content relating directly to the priorities set out by the Elective Recovery Diagnostics team. For these reasons, excerpts from the pathology report have not been included in this guide and this report should instead be read in its entirety Layout 1 (gettingitrightfirsttime.co.uk) | This GiRFT publication aligns to a number of elements within the Wales National Diagnostics Strategy including workforce redesign Additionally, the publication also focusses on the clinical pathway service users of the hubs (Respiratory, Diabetes, MSK, Cardiology and other services) for the elective recovery Alignment of workforce to Wales Diagnostics Recovery and Transformation - Significantly increase the training pipeline of diagnostic specialists including advanced practitioner roles (e.g. reporting biomedical scientists, reporting radiographers, advanced audiology primary care practitioners) and consultant grade roles (e.g. consultant clinical scientists) as part of the service redesign. Please see the annexe ‘GiRFT Diagnostics delivery guide for Imaging workforce redesign detail |  |
| 6. | Open Access Government digital publication quarterly-May 2022 | Staffing the community hubs will be a challenge. The Department of Health and Social Care has said the 100 centres planned by early 2025 will need an extra 3,500 radiographers to carry out diagnostic tests and 2,000 radiologists to interpret the results, as well as 500 advanced practitioners – radiographers with additional training to report on images. The Society and College of Radiographers claims the extra 6,000 specialists do not exist and says the centres will be staffed with people who are only available because they have left jobs elsewhere in the NHS. The Royal College of Radiologists has warned this could have a knock-on effect on waiting times for tests in hospitals – creating a new bottleneck that could delay the start of treatment and potentially lead to poorer outcomes for patients. |  |
| 7. | Topol Review: February 2019 (TOPOL) Preparing the healthcare workforce to deliver the digital future – an independent report on behalf of the Secretary of State for Health and Social Care HEE-Topol-Review-2019.pdf | The workforce is changing with new expectations and the need for a good work-life balance through flexible careers. The NHS Long Term Plan identifies the need for more healthcare workers to respond to this increasing demand. Digital healthcare technologies, defined as genomics, digital medicine, artificial intelligence (AI) and robotics, should not just be seen as increasing costs, but rather as a new means of addressing the big healthcare challenges of the 21st century. This review anticipates how technological innovation will impact the roles and functions of healthcare staff over the next two decades. These technologies will not replace healthcare professionals but will enhance them (‘augment them’), giving them more time to care for patients. Some professions will be more affected than others, but the impact on patient outcomes should in all cases be positive. Patients will be empowered to participate more fully in their own care. Within 20 years, 90% of all jobs in the NHS will require some element of digital skills. Staff will need to be able to navigate a data-rich healthcare environment. All staff will need digital and genomics literacy. This Review is about both the existing and the future workforce. Using AI-based technologies, automated image interpretation in radiology and pathology will lead to faster diagnosis, while speech recognition has the potential to free up more staff time to deliver care. Patient benefit should be the driving force behind AI and robotics design, with new products co-developed with patients from design to implementation. However, it is critical that the healthcare system prepares to adopt any new technologies in a spirit of equality and fairness. A range of social determinants affect health outcomes, and digital health technologies should redress not reinforce inequalities, with particular attention given to vulnerable and marginalised groups. An evolving health workforce There is a need to raise awareness of genomics and digital literacy among the health and social care workforce, which will require development of skills, attitudes and behaviours in order to become digitally competent and confident. This will present new career opportunities for some of the workforce. Genomics will become integral to all specialties. While some aspects will remain with highly specialised professionals, many will become mainstream and embedded in routine healthcare delivery. The health workforce will play a key role in ensuring that genomic technologies are efficiently, appropriately and equitably deployed, so that individuals can understand how genetics can affect their health. Artificial intelligence will be deployed to augment the skills of the NHS workforce. Staff will need to understand fully the issues of data validity and accuracy. Early benefits of AI and robotics will include the automation of mundane repetitive tasks that require little human cognitive power, improved robot-assisted surgery and the optimisation of logistics. NHS organisations should invest in their existing workforce to develop specialist skills. Accredited continuous professional development (CPD) and flexible on-going training and career opportunities, including portfolio careers in academia or industry, will be important to deliver change. Successful implementation will require investment in people as well as technology. To engage and support the healthcare workforce in a rapidly changing and highly technological workplace, NHS organisations need to develop a learning environment in which the workforce is given every encouragement to learn continuously. We must better understand the enablers of change and create a culture of innovation, prioritising people, developing an agile and empowered workforce, as well as digitally capable leadership, and effective governance processes to facilitate the introduction of the new technologies, supported by long-term investment |  |
| 8. | Cancer Diagnostic Workforce – Moondance Report (2023) Diagnostic workforce ¦ Moondance Cancer Initiative (moondance-cancer.wales) | This expert review from Professor Alison Leary was commissioned by the Moondance Foundation. It sets out some of the challenges around current workforce planning approaches. - Higher workloads in terms of volume and complexity and perception that IT and Diagnostic capacity are under-resourced putting the diagnostic workforce under significant strain. - Direct service delivery v. service improvement tension. - Growing demand for diagnostics is not unique to cancer care. - Uncertainty around the design and workforce implications of new diagnostic provision i.e. Diagnostic Hubs and concern that more strategic planning is required. - Potential to contemporise approaches to workforce policy and planning from older models being used. |  |
| 9. | ‘Why do Diagnostics matter? Maximising the potential of Diagnostic services’ The Kings Fund (Oct 2022) Why do diagnostics matter? ¦ The King's Fund (kingsfund.org.uk) | This paper sets out why policy makers have singled out Diagnostics for greater focus as it has a pivotal role in supporting systems recovery through reducing waiting times and earlier cancer diagnosis. The report notes increasing demand across almost all aspects of diagnostics growing at 4-7% each year and the scope for innovation through the introduction of new technologies, widening access and changing patient pathways. Growth in diagnostic workforce has not kept pace with demand and there are significant staff shortages across all specialties but with Radiology, Pathology and Endoscopy notably under strain. The introduction of Community Diagnostic Centres has brought challenges from a workforce perspective with those working in this area highlighting that there is a need for a diagnostic workforce strategy that includes the community diagnostic centres to ensure that the centres can perform the range of tests needed to meet their local population health needs. Without it, staff shortages and skills gaps will undermine the community capacity that community diagnostic centres aim to create. There is scope for artificial intelligence to benefit diagnostic pathways by supporting reporting and reducing the workforce time needed, but this will require significant upfront investment and evaluation to ensure accuracy. There are 29 pathology networks now in place across England and diagnostic imaging networks are set to follow by 2023. The rationale for Networks is the potential for improvement through pooling resources and using the existing equipment, facilities and workforce more efficiently. The report includes a whole section on challenges facing Diagnostics, of which workforce is a major issue along with equipment, facilities and digital capability. Years of poor workforce has led to significant shortfalls in Radiology and Pathology roles and recognises that new ways of working i.e. skill mix are key to delivering services within current workforce capacity. |  |
| 10. | Kings Fund-Keeping People out of hospital: the potential of diagnostic testing in innovating patient pathways-June 2023 Keeping people out of hospital ¦ The King's Fund (kingsfund.org.uk) Catch up free on demand until 7th July 2023 | This free online event considers the wider system Correspondingly, workforce should be considered as to POC analysis and training of primary community resources to utilise POC for admission avoidance e.g. home devices and other locations e.g. virtual wards, In the context of the complex challenges across the health and care landscape, including significant workforce shortages and limited clinical capacity, this event considered the role of diagnostics in supporting those working in the system and keeping people out of hospital. - the potential that increased access to diagnostic testing, and in particular in vitro diagnostic testing, in primary care, the community and in community diagnostic hubs offers to diagnosing people earlier and avoiding unnecessary hospital admissions - what innovations in patient pathways mean for those working across the system and how they are being supported to make changes, in the context of the significant challenges they are facing - the role integrated care systems can play in developing diagnostic services that encourage innovation and are designed with people and communities at their heart. |  |
| 11. | The National Clinical Framework Wales May 2021 National clinical framework: a learning health and care system ¦ GOV.WALES | Diagnostics is only referenced in passing in this Framework but the priorities that it highlights from a workforce perspective apply. It defines workforce as one of the five criteria for reconfiguring services (which is one of the areas of focus in the Diagnostics Strategy for fragile services) when ‘the workforce required to safely and sustainably deliver the service is not available because it cannot be recruited, developed or retained or can only be delivered by a dependency on agency and locum staff’. It gives the action to make the most of all clinical disciplines to deliver more sustainable workforce models and suggests that some of the specialist need can be met and capacity created by staffing groups focussing on doing only what they can do i.e. working at the top of their licence and through the development of advanced practice such as in healthcare scientists. | Almost all clinical pathways have a diagnostic element so the work of the proposed new clinical networks will impact on all diagnostic pathways |
|  | The Kings fund- Two years on, how are community diagnostic centres doing? October 2023 Two years on, how are community diagnostic centres doing? ¦ The King's Fund (kingsfund.org.uk) | This article from the Kings fund examines the impact of community diagnostic centres (CDCs) in England since they were first announced in October 2021. It identified that 127 of the 160 centres promised by 2024 had so far been opened. The governments plan was for these centres to deliver up to 17 million tests by March 2025. Since data of CDC activity was first published in March 2023, CDCs have undertaken 717,270 tests. The article points out that in August 2023, only 6.3% (139,000) of all tests carried out were done in a CDC. The article suggests that these figures could be due to the workforce situation. In 2022, the Royal college of Radiologists found that 89% of CDCs are staffed with existing trust employees who rotate between the CDC and acute sites. They suggest that this scenario may be diluting capacity in both settings. Despite this, the article suggests the CDCs may be contributing to retention of existing staff with feedback that they provide a ‘positive environment’ with ‘better working hours’. | Introduction of CDCs in Wales would need to ensure that there is sufficient workforce supply with the appropriate skills to ensure capacity within acute sites is not negatively impacted. |
| Profession specific documents |  |  |  |
| Ref | Key documents | Key reference points, actions and priorities for diagnostic workforce planning | Relevance to workforce plan |
| 12. | Statement of Intent: Wales Pathology Services (2019) pathology-statement-of-intent.pdf (gov.wales) | The Pathology Statement of Intent identified eight priority areas where new strategic approaches are required to facilitate the development of high quality, effective and resilient Pathology services, of which workforce is one. Pressures on workforce due to growing demand and difficulty in modernising the Pathology workforce due to recruitment, retention and resource availability. Highlighted that many pathology specialties face shortages in Wales, both in medical and scientific professions, with significant challenges in recruiting Biomedical Scientists. Need for a consistent approach to this national challenge, with UHBs working together to overcome problems. Data from the Royal College of Pathology Wales Regional Council Workforce Report for Histopathology highlights the fact that 26% of Consultant posts are vacant. Seven day services, an ageing population and advances in personalised medicine mean that demands on pathology services will continue to increase. As training for medical and scientific professionals within Pathology takes between three to ten years it is important that the investment in training and education includes provision for new trainees, post qualification, registration and continued professional development. Opportunities for developing the scope of practice of healthcare scientists across all specialities within Pathology. It is increasingly recognised that prudent, cross-discipline and flexible skill-mix approaches are needed for future workforce models to meet gaps in skills and expertise and facilitate retention/development. More robust national workforce intelligence is required to help model future needs of Pathology services. Similarly, national approaches to job descriptions, plans and advanced practice, broadening access and mobility within professions are required. The Statement highlights three workforce specific actions: - NHS Wales will support the adoption of prudent, cross discipline and flexible skill-mix approaches to future workforce models, overcoming professional and specialty boundaries by strengthening skills and expertise, increasing attraction and retention of professions within Pathology. - HEIW will support the development of targeted strategies, in conjunction with the Healthcare Science – Looking Forward, framework to facilitate the development of a modern workforce for Pathology Services in Wales. - HEIW and NHS Wales will support the development of information to provide clarity regarding services and workforce to assist with robust future workforce planning and analysis and outline plans to build and consolidate the clinical and scientific base in NHS Wales Pathology Services. |  |
| 13. | Statement of Intent: Wales Imaging (2018) imaging-statement-of-intent.pdf (gov.wales) | The Imaging Statement of Intent sought to address the challenges in diagnostic and therapeutic imaging in the Welsh National Health Services by implementing a coordinated approach, establish a national plan and configure service models to enable sustainable services that provide the best outcomes for Welsh patients. The Statement outlined how services are provided by a wide range of different specialty and professional groups which are under increasing pressure with major growth in demand as a result of more effective clinical pathways, increasing numbers of older people, increasing cancer incidence and improved technology and new techniques. It advised that whilst Clinical imaging was a popular specialty for medical trainees, training capacity did not match current workforce deficits. Wales has seven radiologists per 100,000 population, compared to a European average of 12, and the 160 whole time equivalent consultant workforce in Wales has the oldest demographic in the United Kingdom; based on a retirement age of 62 years, 26% are anticipated to retire by 2020. The professions of radiographers and sonographers are both on the UK shortage occupations list. Workforce Development was a key priority of the Statement with three specific actions: · The NHS Wales Imaging Academy will be established to develop a sustainable and flexible imaging workforce to deliver a modern, responsive diagnostic imaging service for Wales · Health Education and Improvement Wales will facilitate the development of an integrated workforce training strategy for Radiologists, Radiographers, Sonographers, Advanced Practitioners, Assistant Practitioners and other Imaging Healthcare Professionals in Wales. · Welsh Government, in conjunction with NHS organisations, will establish funding models to allow the delivery of a national approach to workforce training that is appropriate for modern, flexible training combined with regional service provision. | The first action has been fulfilled from a Radiologist perspective. |
| 14. | National Endoscopy Programme Action Plan (2019) and National Endoscopy Programme Revised Action Plan (October 2020) WG_Label_Pantone_342 (gov.wales) national-endoscopy-programme-revised-action-plan-october-2020_0.pdf (gov.wales) | Workforce training and development is one of the four Endoscopy Board subgroups with the aim to support local workforce analysis, job planning, recruitment and retention and develop national training and development opportunities. The revised action plan advises that the following workforce actions have been completed: - Map local staffing profiles - Scope requirement for training of all groups of staff - Development of a coordinated national training programme for the clinical endoscopists and commence recruitment to it With further actions ongoing: - Establish standard unit staffing profile - Establish the training faculty to support delivery of the National Endoscopy Training Programme - Develop and begin to implement a national workforce plan for endoscopy. Develop and issue guidance on job planning for medical staff |  |
| 15. | UK Genome Strategy (2020) Genome UK: the future of healthcare - GOV.UK (www.gov.uk) | The UK Genome Strategy sets out a 10 year programme to create the most advanced genomic healthcare system in the world, underpinned by the latest scientific advances, to deliver better health outcomes at lower cost. The focus of this strategy is at a UK level (which differs from other areas of health policy) and signals that the UK intends to work on a 4 nations basis to deliver the ambitious strategy. The strategy focusses on 3 key areas: - Diagnosis and personalised medicine - Prevention - Research. Diagnosis and personalised medicine: This signals an intention to incorporate the latest genomics advances into routine healthcare to improve the diagnosis, stratification and treatment of illness by: - Offering whole genome sequencing as part of routine care - Pharmacogenomics – to enable patients get the treatment and advice that work for them including tailoring drug treatments - Cancer – a new operating model for cancer ensuring multi-disciplinary teams can draw on a range of genomic, imaging and longitudinal health and care data to improve patient outcomes. In terms of prevention, the focus is on: Enabling predictive and preventative care to improve public health and wellness. We will focus on the role genomics can play in: - expanding screening in early life: the UK is uniquely positioned to conduct a high quality, large-scale research programme to determine whether and how sequencing should be implemented for screening in newborns. We will study the opportunities, risks, ethical issues, and regulatory implications of such a programme, ensuring that we progress a public conversation to generate better understanding of patient and public attitudes. - targeted screening: using genomics to improve population health through improved disease prevention including better screening. This includes the use of personalised and risk stratified screening and testing of the family members of cancer patients to identify where they are at increased risk of cancer. We also expect to see development of non-invasive prenatal testing using sequencing to identify diseases. On research: supporting fundamental and translational research and ensuring a seamless interface between research and healthcare delivery. There are also 5 cross cutting themes: - engagement and dialogue with the public, patients and our healthcare workforce, placing the patient and the diverse UK population at the heart of this journey. - workforce development and engagement with genomics through training, education and new standards of care. - supporting industrial growth in the UK, facilitating entrepreneurship and innovation for projects and companies of all sizes, through common standards, funding, procurement, and R&D structures - maintaining trust through strong ethical frameworks, data security, robust technical infrastructure and appropriate regulation. - delivering nationally coordinated approaches to data and analytics. This will enable healthcare professionals and approved researchers to easily access and interpret our world-leading genomic datasets. The strategy is UK-wide, but it is important to note the differences in the evolution and development of genomics in healthcare across the 4 nations. Since health is devolved, decisions about whether and how to implement specific elements of this strategy will necessarily be made separately by the 4 administrations. These decisions will differ to accommodate the different needs of the populations in the 4 nations and the structures and systems of the NHS in each administration. This brings great opportunities for sharing of expertise and best practice, but also some challenges, in particular around data sharing and equity of access. |  |
| 16. | Genomics Delivery Plan (2022) Genomics Delivery Plan for Wales (gov.wales) | Through the strategy, WG aim to create a sustainable, internationally competitive environment for genomics and precision medicine to support the delivery of prudent healthcare for the population of Wales. This will: - be based on all-Wales NHS genetics and genomics laboratory and clinical services, working to internationally recognised standards, as part of an integrated clinical and academic infrastructure for translational genomic medicine - be flexible and able to adapt to rapid change and new technologies, building on excellent relationships, within and beyond Wales, to capitalise on the potential of collaborative working between the NHS, public health in Wales, academia, industry and the citizens of Wales - contain plans to develop the NHS workforce to support the delivery of precision medicine - create a framework to forge new strategic partnerships, to maximise and accelerate health and economic benefits, including inward investment - outline our ambition to be a major contributor to the UK genomics capacity, working collaboratively across borders to obtain the maximum benefit and value for money from developments in genomic technologies - capture the potential of genomic data for Research & Development through supporting Wales’ involvement in world-leading clinical research and trials. | Genomics is a rapidly advancing area of medicine and will impact significantly on patient pathways over the next decade. It is likely that in future there will be more genetic testing requested by primary care and therefore more counselling required. Patient pathways and treatment options will change which means that primary care will need to have a level of understanding of genomic medicine that may be over and above existing knowledge base. |
| 17. | Imaging Workforce Plan – Wales (2023) executive.nhs.wales/networks/programmes/national-imaging-programme/strategy-for-developing-a-radiology-workforce-for-wales/imaging-strategy-docs/strategy-for-developing-a-radiology-workforce-model-for-wales/ | The ‘Strategy for Developing the NHS Wales Radiology Workforce’ was developed by the Imaging Workforce and Education Group (IWEG) in collaboration with Health Education and Improvement Wales (HEIW) and Radiology Services across NHS Wales. This strategy: - Describes the Current shape of the workforce that is employed by Radiology Services in Wales - Describes the significant challenges that are currently being faced by the Radiology workforce - Puts forward a number of potential workforce solutions to assist those involved in the local planning and management of radiology services in Wales - Outlines 22 recommendations to support and facilitate the development of the Radiology Workforce - Sets out a shared vision for a strong, resilient, and sustainable Radiology Workforce for Wales |  |
| 18. | Quality Assurance Agency (2023) Biomedical Science and Biomedical Sciences, and Biosciences Subject Benchmark Statements https://www.qaa.ac.uk/the-quality-code/subject-benchmark-statements/subject-benchmark-statement-biomedical-science-and-biomedical-sciences] | This new Statement offers clarification between Biomedical Science and Biomedical Sciences courses for the first time. It encompasses the broad range of disciplines in Biomedical Sciences and the specific disciplines in Biomedical Science including new technologies, excellence in clinical practice and research-informed teaching, and innovative teaching delivery. Importantly, it also reflects the subject’s strengthening attention to equality, diversity and inclusion, and sustainability. We hope that the revised Statement will provide the framework to support the delivery of future-proofed Biomedical Science(s) programmes across the UK and drive excellence in this field. |  |
| 19. | IBMS, RCPath and ACBLM (2023) Point of Care Testing National Strategic Guidance https://www.ibms.org/resources/news/national-poct-strategy/] | Point of care testing (POCT) testing can be defined as those tests performed with equipment operated outside of a laboratory environment, from patient wearables and lateral flow devices, for example pregnancy tests and covid LFD’s, to ward-based multianalyte devices. The purpose of a POCT service is to enable the delivery of high quality, accessible diagnostics at the point of need for clinical services, improving clinical outcomes and enhancing the patients’ healthcare experience Healthcare is changing as technology develops, more virtual and remote (from the traditional healthcare setting) models of care are emerging. These models are changing the demands of traditional services, and a clear demand is for more diagnostics to be delivered at the point of need. There are further areas where POCT is expanding to include population health screening and diagnostic testing access for hard-to-reach social groups. | The NHS England Long Term Plan and the Richards review highlights the importance of patients receiving care closer to home, shifting from acute hospital-based services towards more adaptive community-based settings. |
| 20. | Broader pathology guidance: - International Organization for Standardization (2022) ISO 15189:2022 Medical laboratories – Requirements for quality ad competence [Accessed at: https://www.iso.org/standard/76677.html] - NICE (2014, updated 2023) Acute kidney injury quality standard [Accessed at: https://www.nice.org.uk/guidance/qs76] IBMS have commented - NHS England (2023) Improving the Blood Culture Pathway [Accessed at: https://www.england.nhs.uk/publication/improving-the-blood-culture-pathway-executive-summary/] | These documents set out specific guidance that for individuals working within pathology services. |  |
| 21. | Physiological Measurement workforce and education: Royal College of Physicians (2020) Recognising the vital role of healthcare scientists, clinical physiologists and technologists https://www.rcplondon.ac.uk/news/recognising-vital-role-healthcare-scientists-clinical-physiologists-and-technologists | This brief paper recognises the vital role that healthcare scientists, clinical physiologists and technologists played during the pandemic, particularly in respect of extending their roles to cover gaps created when medical staff were allocated to other duties. | It highlights the potential for the skills of these professionals to be deployed more widely in the NHS |
| 22. | Audiology: British Academy of Audiology (2022) NHS Lothian Report https://www.baaudiology.org/nhs-lothian-full-baa-statement-and-reports/] NHS England (2022, updated 2023) Audiology Systematic Improvement: https://future.nhs.uk/gf2.ti/f/1359778/154210469.5/PDF/-/Audiology%20Systematic%20Improvement%20Final_Minor%20update%20March%20_23.pdf Scottish Government NHS Lothian Review (2023): Independent Review of Audiology Services in Scotland - gov.scot (www.gov.scot) | The British Academy of Audiology Independent Review into the Paediatric Audiology Service at NHS Lothian has found systemic failings which led to some babies and children being undiagnosed or significantly delayed in diagnosis and appropriate treatment. “The root cause of these failures were a lack of scientific leadership, knowledge, reflection and enquiry in the presence of a lack of routine and robust quality assurance processes.” – personal note: Lack of suitable education and training was particularly implicated. |  |
| 23. | Neurophysiology: British Society for Clinical Neurophysiology (publication date not clear – website updated 2023) Guidance on Clinical Reporting [Accessed at: https://www.bscn.org.uk/content_wide.aspx?Group=guidelines&Page=guidelines_home] https://www.bscn.org.uk/data/files/Guidelines/Guideline_resources.pdf | This details how Consultant Clinical Scientist Neurophysiology roles may be supported. Physiologists in NHS Wales are at a stage of developing towards being able to undertake such roles, such as undertaking the formal Higher Scientist Specialist Training. Also includes detailed list of standards and resources. | Note that the Healthcare Science Programme are working with WHSSC to bring into national commissioned approach in April 2024 |
| 24. | Echocardiography: The UK echocardiography workforce (2023) (bsecho.org) British Society of Echocardiography January 2023 | The British Society of Echocardiography commissioned Professor Alison Leary and Dr Geoff Punshon to develop this report looking at workforce issues with echocardiography. There is significant increased demand for the echocardiography labour market but, as a result of the long lag time to train individuals to the high standards necessary to safely perform the diagnostic test, there is no way to liberalise quickly and safely the supply required. This makes retention of the existing workforce key along with education of the next generation and liberalising the returner labour market. Echocardiography lacks career structure, job planning and clear routes to progression. This has also resulted in the workforce focussing on direct clinical work and not having the capacity to do important quality assurance and safety work, service development work or train the next generation. There are issues with workflow into the echocardiography services such as non-standardised referrals and lack of data integration or services to share imaging or clinical information. Focusing on, and offering attractive and distinct roles to, experienced returners, such as supporting quality improvement, teaching opportunities, and such roles could offer a more predictable workload. Investing in practice facilitation or specific clinical educator posts running parallel ‘service’ and ‘workforce development’ lines could be prioritised. There is an opportunity to help deal with over work issues by introducing skilled supplementary workers and a support workforce in order to redistribute work such as administrative work. The recommendations of the review are: - Support in implementing a formal national career pathway in echocardiography to make services sustainable. - Recognise the advanced level role of an echo educator - Enable diagnostics by increasing training capacity and utilising new models such as introducing a slow lane and attracting returners. - Develop new roles which help distribute work such as administrators, data managers and support workers. | The recommendations are relevant to both HEIW and employers. |
| 25. | England GiRFT National Pathology Report-September 2021 Statement of support from Royal College Pathologists Layout 1 (gettingitrightfirsttime.co.uk) | The pathology workforce is primarily made up of medically qualified pathologists, clinical scientists and biomedical scientists, working in multidisciplinary teams (MDTs) across the pathology specialties. According to recent statistics, in the UK there are: 22,000 biomedical scientists, ranging from trainees to advanced clinical practice or consultant-level staff, along with high-level operational and service managers; 3,575 pathologists, including consultants, specialist registrars, and junior doctors; 264 consultant clinical scientists, with an equal number of trainees and other grades of clinical scientist. Workforce GiRFT National Pathology Recommendations: Identify and close workforce gaps at a national level - Building on network-level metrics identifying gaps, the NPB to work with training bodies and Health Education England (HEE) to ensure a wide range of intake and increase the number of training positions available, to meet anticipated future demand. b Labs, trusts and PNs to allocate time for biomedical scientists to mentor and tutor colleagues to higher levels to fill gaps in the medical workforce in all relevant specialties (within 2 years of publication of GiRFT National Pathology report-Sept 2021) - The urgent need for widespread introduction of digital pathology within histopathology is recognised See Annexe for Pathology workforce detail with all the Pathology professions |  |