## Toolkit - Main Menu
Version 1 June 2021
Health Education and Improvement Wales
An Interactive Toolkit to Support Workforce Planning
Alongside each step you will find useful resources, depending on the type of plan you are developing you can select those that best support your plan
Click on the links below to jump to each section
Our Approach to Planning | 1. Define Your Plan | 2. Map The Service Change | 3. Define the Workforce | 4. Understand Workforce Supply | 5. Define Required Actions | 6. Implement and Monitor
| Your Plan Summary |  | Your Staff Profile |  | Link to HEIW Resources (Currently in development, all resources are available in the accompanying E-Resource Book as an interim measure)

## Our Approach to Planning
Back to Main Menu | HEIW Toolkit to support Workforce Planning
OUR AMBITION | "By 2030, we will have a sustainable workforce in sufficient numbers to meet the health and social care needs of our population" | Workforce planning in NHS Wales is based on the Skills for Health Six Step Methodology. In secondary care it is linked to the requirements of the Integrated Medium-Term Plans (IMTPs). In primary care, this approach has been adapted for use in Clusters and to support the requirements of Cluster Integrated Medium-Term Plans. This toolkit will help in the development of local workforce plans in applying the six steps methodology.
Source: A Healthier Wales - Workforce Strategy for Health and Social Care (click to view)
The six step model fits within the NHS Wales Planning Framework and can support development of Operational Plans in the short, medium and longer term | Short Term Planning up to 12 months ahead | Medium Term Planning up to 3 years | Long Term Planning up to 10 years
| Could also be described as establishment monitoring, typically includes headcount, budget management and is usually reactive to immediate service demand. | Likely to be linked to IMTP planning, focusses on workforce required to meet IMTP aims and objectives. Typically includes planned recruitment, succession planning, and organisation change plans. | Usually developed to meet longer term strategies. Typically includes scenario planning for future service models, longer term projects, predictions in availability of future workforce, increasing demand for services aligned to population changes.
Workforce Planning is not an add on it is a part of every Leader / Managers job
The workforce needs to be flexible across organisational and professional boundaries
Workforce Planning needs to be based on what skills and competencies are needed
60% of the future workforce are already in post

## 1. Define Your Plan
Back to Main Menu | Step 1 - Define your Plan
| Clarify the rationale and scope of your plan. Be clear on why a workforce plan is required, what the scope of your plan is and what it will be used for. This is the critical first step in any planning process. You must be clear why a workforce plan is required and what it will be used for. You must determine the scope of the plan, whether it will cover a single service area, a particular patient pathway or a whole health economy and given this, be clear who is responsible for ensuring the plan is delivered and who else will need to be involved in the planning process. | Potential Outputs at this stage:- Project Initiation Document (PID) - Commenced Stakeholder Analysis PEST Analysis SWOT Analysis Impact Assessment (s - Commenced Risk Assessment - Commenced Strategic Workforce Plan - Commenced
| Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
| A SWOT Analysis is when you look at your organisations Strengths, Weaknesses, Opportunities and Threats and can help to identify what could impact on your plan. | Do you know who all your stakeholders are? a Stakeholder Analysis can help you to identify who you need to engage with in developing your plan.
| A PEST or PESTEL Analysis helps to consider the Political; Economical; Social; Technical; Environmental and Legal aspects and help to identify what is influencing your plan. | An Impact Assessment can help you to identify any issues that you need to address e.g. equality impact, privacy impact, quality impact.
| Your IMTP is NHS Wales Integrated Medium Term Plan, you may also have an Annual Plan or Service Plan for your department that you need to consider. | You will need to consider what the Risks are, you may have identified these in your SWOT and impact assessments. Does your organisation have a Risk Management Process that you need to follow?
| A Project Initiation Document (PID) provides an outline of your project. Many organisations will have a template for a tailored PID, if not there is a Project Resource available. | A Strategic Workforce Plan Template is available if you are using this toolkit to help develop your Strategic Workforce Plan
| What Strategy or Initiative documents do you need to think about for your workforce plan? e.g. A Healthier Wales, Digital Wales, what is your organisations strategy? | What Policies do you need to consider e.g. NHS Wales Policies, Organisation Policies
| Do you participate in Peer Reviews, Quality & Safety Reviews, Staff Surveys or Service User Experience Feedback? use Feedback from these to identify improvements, benefits and issues for your workforce plan | If you are developing a longer term strategic plan you will probably need to think about the 'what if' and undertake future Scenario Planning e.g. to identify advances in technology, new treatments or potential increased numbers of service users.
What you need to include | Things to consider:- | Define Your Plan - use this space to make notes (this information will automatically be added to your workforce plan summary)
Plan Purpose | ● Why are you doing this? What are you trying to fix? ● What is driving this change? - Is it a change in service, or a new service? - Do you need to change the way things need to be done? - Is it because of external influences such as Government Policy or Strategy? ● What are the goals/aims/objectives of the plan? ● What will the plan enable you to do? ● Who will the plan affect, both directly and indirectly?
Plan Scope | ● What are you considering in your plan? e.g. types of workforce. What is in scope and what is not in scope? ●Can you define what steps you need to take to develop your plan? ● What team/department/service is covered by the plan? ● Who are your stakeholders (internal and external), how will they be affected and how will they be involved? Who do you need to influence?
Ownership | ● Consideration of who owns the plan will ensure the plan is enacted. Who owns the Workforce Plan, is it a team, service or department? ● Do you have a lead person, what help do you need? ● Who needs to be involved both internally and externally? ● How will you engage with the stakeholders, are there already communication channels in place? ● Is everyone involved 'signed-up' to the plan?

## 2. Map The Service Change
Back to Main Menu | Step 2 - Map The Service Change
| This is about the service redesign in response to service user need and/or changes in service delivery. This is the first of three inter-related steps. You must be very clear about current costs and outcomes and identifying the intended benefits from service change. You should identify those things that support the change or may hamper it. There must be a clarity about whether the preferred model better delivers the desired benefits or is more likely to be achievable, given anticipated constraints. | Potential Outputs at this stage:- Project Initiation Document (PID) - Continued Options Appraisal Literature Review/Research Strategic Workforce Plan - Continued Impact Assessments - Continued Risk Assessment - Continued
| Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
You will need to think about current budget, future budget and if you have any cost savings plans. Speak to your finance team who will be able to help you with the Financial aspects of your plan
Do you have any performance measures, targets, outcomes you currently monitor that should be included?
It may be worth thinking about undertaking a literature review or doing some field research. Has anyone already done what you are planning to do? does this help you in developing your plan?
You might want to refer to some national statistics and data. Find some links to Stats Wales, Office for National Statistics and population health information on the HEIW resources page
An option appraisal can help you to evaluate different the options. Your organisation may have it's own process to do this, if not there is guidance available via the HEIW resource page
What you need to include | Things to consider:- | Map the Service Change - use this space to make notes (this information will automatically be added to your workforce plan summary)
Goals/ Benefits of Change | ● What are the benefits to this change? ● Will there a more positive outcome, who for? ● What are the choices? ● What will good look like? Will your workforce feel valued and supported? ● How will this align to the Workforce Strategy for Health and Social Care?
Current Baseline/ Summary | ● What are the current costs and outcomes under the current model? what things are working well? and what are not? ● What are planning to build on? ● What does you staff profile look like? what are your critical workforce points/risks e.g. an ageing workforce, too high turnover, too many specialist posts that can't be covered? Is multi-disciplinary teamworking embedded in your organisation? ● Is there any research that can support you in this mapping? ● Is there any National policies and strategies that could assist you?
Future Model Design, the Drivers and Constraints | ● Challenge the driver(s) and ensure there are benefits to proceeding ● What was the result of your options appraisal? ● Think about the risks ● Does this service change support the Future Generations Act wellbeing goals?

## 3. Define the Workforce
Back to Main Menu | Step 3 - Define the Workforce
| This step involves identifying the workforce needed to deliver the future or reconfigured services. What skills are needed the type of workforce and numbers of staff required. This step involves mapping the new service activities and identifying the skills needed to undertake them and the types and numbers of staff required. This will involve consideration of which types of staff should best carry out particular activities in order to reduce costs and improve the patient experience even where this leads to new roles and new ways of working. | Potential Outputs at this stage:- Skill Mix Analysis Pathway Mapping (Process Map) ESR Workforce Reports Patient Needs Assessment Activity Analysis Research/Workforce Trends Strategic Workforce plan - Contiued Impact Assessments - Continued Risk Assessment- Continued
| Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
| Review your Skill Mix in relation to roles e.g. doctors, nurses, healthcare support workers. HEIW have a tool that can help with this go to the resources page to find the link. | When considering the potential options for Workforce Re-design it may be helpful to analyse the type of work/activity required e.g. new work or existing work to help determine the type of workforce you need.
| Pathway Mapping is a useful tool to help you to analyse what skills are needed for a specific activity. Tasks are broken down into the competences required to meet the patient/service user needs | NHS Wales has developed guidance for delegation, which can help you to design your required skill mix and task redistribution.
| A Patient Needs Assessment in the context of workforce planning is looking at what each patient may need at a point in the patient pathway, this can also be linked to population based needs. | NHS Wales has in place an Advanced Practice Framework for Nursing, Midwifery and Allied Health Professional Staff which can help you to identify advanced practice roles and what development is needed to support them
| Workforce Profile. ESR is the electronic system used across NHS Wales for employee data. Most managers will have access to information and reports via the Business Intelligence Tool. | Your organisation can guide you through the process of role redesign which may include developing job descriptions for your roles. There is specific standards and guidance for NHS Wales covering role redesign.
| HEIW publishes reports on Workforce Trends for NHS Wales, you can find the link for this on the resources page. There may also be other workforce trends outside of NHS Wales related to specific professions that you might want to consider e.g. Society of Radiographers, BMA, RCN | Activity Analysis, this will help to determine what has changed in service demand
What you need to include | Things to consider:- | Define Your Workforce - use this space to make notes (this information will automatically be added to your workforce plan summary)
Activity Analysis | ● What is your activity telling you about your service and your current workforce? has demand changed or are there new activities that require new skills and knowledge? ●What are the key tasks within the new service delivery model? do they meet population/service user needs? ● Have the activities been broken down into tasks, skills, competences and knowledge? Do the right people in your current workforce have the knowledge or skills? ● Do you know your workforce trends (links to your workforce baseline profile), how does your workforce compare to other similar organisations? ● What support do you need e.g. business intelligence support, workforce planning expertise
The New Way of Working | ● Has productivity implications been considered based on technology, patterns of working, clinical and service models, skills mix and/or redistribution of tasks and training requirements? ● Are there any process/system developments that need to be taken into account, new technology, non-staffing considerations e.g. estates/equipment ● Have you considered the here and now as well as the long term future e.g. population needs, sustainability and resilience ● What are the timeframes to consider e.g. training time, leading time for technology and building the digital capability of the workforce
Type and Numbers of Staff Required | ● Have you identified the roles required against the patient/ service user pathway? what type and size workforce do you need? is it multi-disciplinary? ● Is there evidence/research base or regulations that can support you in defining the workforce requirements ● What roles could you introduce? What will the effect of these roles be on other staff? What training or development does your current workforce require? ● Will this affect other services, teams or individuals? What will be the impact? ● What is the size and composition of the workforce needed to deliver the service?

## 4. Workforce Supply
Back to Main Menu | Step 4 - Understand your Workforce Supply
| This step involves identifying the workforce needed to deliver the future or reconfigured services. What skills are needed the type of workforce and numbers of staff required. This involves describing the existing workforce in the areas under consideration, its existing skills and deployment, plus assessing any problem areas arising from its age profile, turnover or other critical workforce points. It may be the case that the ready availability of staff with particular skills, or, alternatively, the shortage of such staff itself contributes to service redesign and steps 2 and 3 will need to be revisited. Consideration should be given to the practicalities and cost of any re-training, redeployment and/or recruitment activities that could increase or change workforce supply. | Potential Outputs at this stage:- Staff Profile Benchmarking Strategic Workforce Plan - Continued Impact Assessments - Continued Risk Assessment - Continued
| Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
| If you haven't already a conversation with your organisations Workforce Planning Specialists who can offer advice and guidance on workforce supply | Identify your workforce supply pipelines e.g. do you know how many students there are in the different professions in Wales? Where does your workforce come from?
| Do you have an organisation Succession Planning Strategy, if not you can find a link to the NHS Wales National Succession Planning Strategy on the HEIW resources page | Your organisation may have in place a Workforce Education Strategy that can help you to plan any training and development requirements for your plan.
| Benchmarking can be a useful way to look at how your organisation compares with other similar organisations. There are also other ways to check e.g. Nurse Staff Levels Act Wales or SCoR Principles of safe staffing. Radiographers. You can also benchmark to see if your workforce is representative of your community using the NHS Employers tool. You find a link to this on the resources page. | What are your recruitment concerns, are your workforce on the Governments Shortage Occupation List?
What you need to include | Things to consider:- | Workforce Supply - use this space to make notes (this information will automatically be added to your workforce plan summary)
Current Workforce | ● What are the skills of the current workforce? Describe the current workforce in terms of numbers of certain types of: staff, skills, competences, services – do you know the current workforce well? ●Are you working effectively now? ●What current vacancies are there within the service area? What impact are these having? Do they represent a significant recruitment issue? ● Do you have any critical workforce points e.g. ageing workforce, small number of specialist staff, limited succession planning, access to suitable education, leadership development? or skills gaps e.g. non-medical prescribing ● Is your workforce representative of your community?
Workforce Forecasting | ● Do you know what skills, training and qualifications are required for the workforce? ● What turnover/attrition is expected? ● What numbers are in the training/education pipeline? ● What influences on supply are there even with no service change (e.g. flexible working trends) ● What is the anticipated competition for skills with other employers in the local/national labour market? Do you know the wider environment and the supply? ● Will this help you to have the right people, in the right place with the right skills?
What are the Options | ● What do you need to ensure resilience and sustainability? ● What options for retention, retraining, recruitment, redeployment etc. can be realistically developed? ● What are the options for expending roles e.g. advanced practice, introducing assistant roles? ● Have the options for working differently been analysed and costed?

## 5. Define Actions Required
Back to Main Menu | Step 5 - Define your Actions
| Your plan for delivering the right staff, with the right skills in the right place needs to be developed with milestones and timescales. This step involves reflecting on the previous 3 steps and determining the most effective way of ensuring the availability of staff to deliver redesigned services, even if this means some further service redesign. You should also include in your plan an assessment of anticipated problems and how you will build momentum for change, including clinical engagement. | Potential Outputs at this stage:- Gap Analysis Action Plan Strategic Workforce Plan - Completed Impact Assessments - Completed Risk Assessment - Completed
| Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
| Many organisations will have Project Management Resources available tailored to their organisations, but there are also project management resources available via the HEIW resources page under Step 6 Implement & Monitor | Is your workforce representative of your community? you can use the NHS Employers tool to benchmark against. Find the link on the resources page
| NHS Wales has in place an Organisational Change Policy. This process supports implementation of change that affects employees and may help you to plan your change | Link to your Workforce Team for Change Management and give consideration to the length of time it will take to achieve the changes you have identified
| There is a basic Action Plan template included in the toolkit on page 6 Implement and Monitor | A Gap Analysis will be needed to consider the current state-v-the future state to identify the gaps so that you can work out actions that will need to be taken to deliver your plan.
What do you need to do? | Things to consider:- | Define your Actions - use this space to make notes (this information will automatically be added to your workforce plan summary)
Gap Analysis | ● Has a gap analysis been undertaken of each scenario? has the gap analysis identified any gaps between demand and supply of your workforce. What changes or action are needed to the current workforce to address the gaps, what about leadership roles and succession planning ● Has the gap analysis identified any new skills, knowledge and competences required for the current and future workforce? ● Have you or do you need to develop job descriptions? Do you need a training plan? or to develop a recruitment plan? or can you opt for a less traditional route (e.g. apprenticeships) ● Have you considered all the equality aspects? is your workforce representative of your community? have you considered the Welsh Language Standards?
Priority Planning | ● What are the most significant areas for change (to reduce the gap in Supply & Demand)? ● What is the cost? Is there a Cost Improvement Plan in place ● What are the least significant areas for change (to reduce the gap in Supply & Demand)? ● Have you considered National Issues – national shortages? ● What are your critical workforce points?
Managing Change | ● Has momentum been built in for change? mandated/endorsed from senior leadership? do you have support from key stakeholders? Workforce, OD? Planners? Financial resources? ● How will momentum and engagement for change be sustained? ● How will you support wellbeing for all those involved in the change? ●What are the risks? ●Are you properly engaged with your stakeholders?

## 6. Implement & Monitor
| Back to Main Menu | Step 6 - Implement and Monitor
|  | Your plan must be delivered effectively and will need periodic review and adjustment. The plan should be clear about how success will be measured. Unintended consequences of the changes can be identified during review so that corrective action can be taken. | Potential Outputs at this stage:- Project Plan Implementation Plan Project Evaluation and Lessons Learned
|  | Tips, Tools and Resources to help you - you will find a range of templates tools and links to useful resources on the HEIW Workforce Planning Resources Page | All Resources and Links can be found in the accompanying Workforce Planning Toolkit E-Resource Book
Project Management Resources, particularly for monitoing and evaluating
| What do you need to do? | Things to consider:- | Implement your Plan - use this space to make notes (this information will automatically be added to your workforce plan summary)
| Implement | ● How are you going to monitor delivery and quality ● How will you monitor risks ● How does this fit into your wider organisation planning requirements (e.g. IMTP)
| Monitor | ● What will you measure? (e.g. Budget; Surveys; Activity; Sickness)
| Evaluate | ● When will you evaluate your plan, how will you manage changes to the plan? How will you know your plan is working? Who will you involve in the evaluation? Did you identify any lessons learned?
Identify the Actions Required
Ref | Lead/ Responsible Person | Key Actions | Risks/Issues

## Your Plan Summary
| Back to Main Menu |  | Your Plan Summary
| Department/Service/Owner |  |  | Date Prepared:
Use the text collected here to build your workforce plan, you can highlight and copy the text into the Strategic Workforce Plan Template.
1. Define your Plan |  |  |  |  | Click here to return to Step 1
| Purpose |  | Scope |  | Ownership
| 0 |  | 0 |  | 0
2. Map the Service Change(s) |  |  |  |  | Click here to return to Step 2
| Goals/Benefits of Change |  | Current Baseline/ Summary |  | Future Model Design, the Drivers and Constraints
| 0 |  | 0 |  | 0
3. Define the Workforce Required |  |  |  |  | Click here to return to Step 3
| Activity Analysis |  | Type and Numbers of Staff Required |  | The New Way of Working
| 0 |  | 0 |  | 0
4. Understand the Workforce Supply |  |  |  |  | Click here to return to Step 4
| Current Workforce |  | Workforce Forecasting |  | What are the Options
| 0 |  | 0 |  | 0
5. Define the Actions Required |  |  |  |  | Click here to return to Step 5
| Priority Planning |  | Gap Analysis |  | Managing Change
| 0 |  | 0 |  | 0
6. Implement and Monitor |  |  |  |  | Click here to return to Step 6
| Implement |  | Monitor |  | Evaluate
| 0 |  | 0 |  | 0
ACTION PLAN TEMPLATE
Ref | Key Actions | Lead | Risks/Issues | By When | Current Status for Monitoring
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0

## Your Staff Profile
Back to Main Menu | Your Staff Profile
Use this blank page to add your staff profile charts and staff lists downloaded from ESR
You may want to think about including:-
ESR Staff Profile Data
You might want to include the following:- ● Staff Whole Time Equivalent and Headcount ● Staff Age Profile ● Skill Mix (staff grade and profession) ● Equality Data ● Working Patterns ● Staff Sickness Rates ● Staff Turnover/Attrition Rates | You can find the ESR Guide in the accompanying Workforce Planning Toolkit E-Resource Book. If you don't have access to ESR you can contact your ESR Team and ask for the information you need. Every organisation is required to publish its equality data on an annual basis, your equality manager will be able to help you find this information.