Confirmed Minutes of the HEIW Board Meeting

held on 18 May 2023 at 11:00am

via Zoom/ Teleconference and Meeting Room 1, Ty Dysgu

Present:

Dr Chris Jones                           Chair

Dr Ruth Hall	Independent Member/Vice-Chair

Gill Lewis 	Independent Member

Tina Donnelly 	Independent Member

Prof. John Gammon 	Independent Member

Donna Macarthur 	Independent Member

Alex Howells 	Chief Executive

Julie Rogers	Director of Workforce and OD and Deputy Chief Executive

Lisa Llewelyn 	Director of Nurse and Health Professional Education

Glyn Jones	Director of Finance, Planning and Performance

In attendance:

Sian Richards 	Director of Digital Development

Angie Oliver 	Deputy Director of Workforce and Organisational Development

Michele Sehrawat	Head of Pharmacy Workforce Planning and Consultant Practice

Christian Favager	IETP Strategic Programme Manager

Margaret Allan	Pharmacy Dean

Helen Cade	Communication and Engagement Manager

Dafydd Bebb	Board Secretary

Huw Owen	Welsh Language Manager

Sarah Griffiths 	Corporate Governance Manager (Secretariat)

| PART 1 | PRELIMINARY MATTERS | Action |
| --- | --- | --- |
| 1805/1.1 | Welcome and Introductions |  |
|  | The Chair welcomed everyone to the meeting and a quorum was confirmed present. The Chair welcomed Donna Macarthur, Independent Member and Glyn Jones, Director of Finance, Planning and Performance to the Board. |  |
| 1805/1.2 | Apologies for absence |  |
|  | Apologies were received from Prof. Pushpinder Mangat, Medical Director. It was noted that Margaret Allan, Pharmacy Dean, was in attendance in his place. |  |
| 1805/1.3 | Declaration of interest |  |
|  | No declarations of interest were received. |  |
| 1805/1.4 | Good News Story: Welsh Language Placement Videos |  |
|  | A selection of Welsh Language Placement Videos was presented to the Board. The videos showed allied health professional students from across Wales and highlighted instances where they had used the Welsh language positively during their clinical placements. The Board welcomed the videos and thanked the learners for their participation. |  |
| 1805/1.5 | To receive and confirm the minutes of the Board Meeting held on 30 March 2023 |  |
|  | The Board received the minutes of the meeting held on 30 March 2023 and confirmed they were an accurate record of the meeting. |  |
| 1805/1.6 | Action Log from the Board meeting held on 30 March 2023 |  |
|  | The Board received the Action Log and noted that all the actions were either complete or in progress. It was noted that action 3003/4.11.1, which related to an ISA315 guide, was still in progress and a training date was in the process of being agreed with Audit Wales for the Executive Team and the Senior Leadership Team. |  |
| 1805/1.7 | Matters Arising |  |
|  | There were no matters arising. |  |
| PART 2 | CHAIR AND CHIEF EXECUTIVE REPORTS |  |
| 1805/2.1 | Chair’s Report |  |
|  | # The Board received the report. Introducing the report, the Chair updated the Board on the range of activities and meetings undertaken by the HEIW Chairman and Vice Chair since the last Board meeting. It was noted that the Welsh Language Student Placement Videos and the Train, Work, Live videos demonstrated how HEIW continued to work towards widening access to education and training and attracting and encouraging to people to come to Wales to ensure a sustainable workforce for the NHS. It was confirmed that the annual review process had been completed with all Independent Members. Two new Independent Members had been appointed to HEIW, Donna Macarthur who joined HEIW’s Board in April and Jane Sadgrove who would be joining in September. It was noted that the Chair had attended the Welsh Government’s Anti-Racism Leadership event. It was confirmed that Ruth Hall had attended a Research and Development Champions Group where members discussed the NHS Wales Research and Development Framework. A Board Development Session would be held in the Autumn to discuss the Research and Development Framework, the organisations and Boards understanding of this and the approach. Members considered and ratified the Chair’s Actions within the report. | DB |
| Resolved | The Board: - noted the content of the report. - approved the appointment of Donna Macarthur as a member of the Audit and Assurance Committee. - ratified the following Chair’s Actions as outlined more fully in paragraph 10 of the paper: Chair’s Action 1 - Chair’s Action undertaken on 30 March to appoint Glyn Jones as Director of Finance, Planning and Performance. Chair’s Action 2 - Chair’s Action undertaken on 30 March to approve a paid bank holiday for the King’s Coronation. |  |
| 1805/2.2 | Chief Executives Report |  |
|  | # The Board received the report. Introducing the report, Alex Howells updated the Board on the range of activities and meetings undertaken since the last Board meeting. It was noted that end of year service reviews had taken place with teams across HEIW. It was confirmed that the Integrated Medium-Term Plan 2023-26 (IMTP) was submitted to Welsh Government and a review meeting took place on 9 May. It was noted that formal feedback from Welsh Government was expected. |  |
| Resolved | The Board: - noted the report for information. |  |
| PART 3 | STRATEGIC MATTERS |  |
| 1805/3.1 | Approval of Strategic Pharmacy Workforce Plan |  |
|  | The Board received the final plan. Introducing the report, Margaret Allan highlighted that extensive work had taken place over a twelve-month period to develop a plan in consultation with partners which now required Board approval. In presenting the report, Michele Sehrawat confirmed that following the draft plan being submitted to the Board in January, a consultation had taken place and responses recorded a high level of support for the proposed actions. Thirty-one actions were included within the plan in aligned with the seven themes of the Workforce Strategy. It was highlighted that the Board had previously considered the development of the plan at a Board Briefing in January 2023. The Steering Group signed off the draft plan in May 2023. The plan was then approved by the Executive Team in May 2023 subject to amendments which were then actioned. It was confirmed that discussions around the cost of implementation, actions and funding were in progress. It was noted that conversations would take place with partners over the summer period regarding the implementation plan. Subject to Board approval, the intention was for the plan to be formally launched on 30 June 2023. The Board sought reassurances on implementation of the plan, which included the resources available and whether once implemented the plan would address the high attrition rates in pharmacy. It was suggested that the public should be informed of the plan at an early stage. It was noted that resources to deliver on the plan would be included as part of the costed implementation plan. The Board also sought assurances on workforce data and the need to ensure a clear understanding of the workforce in Wales to be able to plan effectively to inform commissioning. It was highlighted that GP practices used a workforce tool, Wales National Workforce Reporting System (WNWRS), and this was being rolled-out to include community pharmacy to provide missing workforce data. It was confirmed that a detailed plan for next phase was in place which included draft implementation actions and stakeholder involvement. It was suggested that the Board be provided with a further report on the detail of the implementation arrangements once the work to finalise the costed implementation plan has been completed. The Chair asked for a list of key points from the Strategic Pharmacy Workforce Plan to be included in a letter to the Minister. The Board welcomed and supported the plan and congratulated the team on the work undertaken. | PM |
| Resolved | The Board: - approved the Pharmacy Workforce Plan in light of the consultation. - noted the intention for a formal launch event on 30th June. - supported the development of a costed implementation plan by September 2023. | PM |
| 1805/3.2 | People and Organisational Development (OD) Strategy 2023-2026 |  |
|  | The Board received the report. Introducing the report, Julie Rogers confirmed that the strategy had undergone significant consultation since the first draft was shared with the Board in a Board Development Session in February. It was confirmed that the paper shared with the Board was the final draft. Thirty-eight objectives for 2023-26 were included in the plan which were set under seven themes aligned to the Workforce Strategy for Health and Care. It was confirmed that implementation progress updates would be shared with the Board and that the aim was for the Strategy to be formally launched at the Staff Conference in June 2023. It was confirmed that engagement had taken place with the sessional workforce and that a number of actions were included in the strategy in this area. The Board was advised that updates on the implementation would be provided through the IMTP quarterly performance framework reporting and annual reporting to the Board. The Board welcomed the report and thanked Rhiannon Williams, Foula Evans and teams for their work. | JR |
| Resolved | Members approved the final draft of the People and OD Strategy 2023-2026. |  |
| 1805/3.3 | Update on Strategic Mental Health Workforce Plan (SMHWFP) |  |
|  | The Board received the report. In presenting the report, Angie Oliver provided an update on the progress in implementing the Strategic Mental Health Workforce Plan (SMHWFP). It was confirmed that a full draft implementation plan had been developed and that plans were in place to spend the full funding allocation for 2023-24. It was highlighted that the first costed SMHWFP for health and social care had been submitted to Welsh Government in June 2022. Welsh Government had approved both education and training and workforce and OD elements of the proposed budget and agreed to support the full resourcing of the costed plan. Since the launch of the plan in November 2022, a number of actions had been progressed in areas of education and training, new workforce models and attraction and recruitment. It was confirmed that a Multi-stakeholder Implementation Board had been meeting monthly since December 2022. It was highlighted that professions were being upskilled to be able to use the strategy in practice. It was confirmed that the plan was developed and implemented in partnership with Social Care Wales. It was confirmed that a Retention Guide was being developed for the whole workforce, being led by the team developing the Strategic Workforce Plan for Nursing. It was suggested that progress on the implementation should be reported externally, and that learning should be captured. Discussions had taken place regarding commissioning an independent evaluation of the strategy. The Board welcomed the report and thanked the team. |  |
| Resolved | Members: - noted the paper which was provided for assurance. Given the importance of this work a further update would be provided in Q4 23/24. - It was agreed that the development of the retention guide to be presented to the Board in June/July 2023. | JR LL |
| 1805/3.4 | HEIW Resource Plan 2023-24 |  |
|  | The Board received the report. Introducing the report, Glyn Jones highlighted the approach taken to establish the 2023-24 budgets delegated to budget holders in line with the Integrated Medium-Term Plan 2023-26 (IMTP). It was noted that HEIW had established a 2023-24 Resource Plan, based on the 2023-26 IMTP, which set out the basis for setting a balanced financial plan and delegation of budgets. It was noted that HEIW had a statutory duty to break even at the financial year end. To ensure the duty was achieved, delegated budgets were established. Expenditure against agreed budgets was routinely monitored as part of effective budgetary control and financial governance. The total funding allocated was £327.41M. It was confirmed that the finance team would be assessing risk and opportunities around financial resources throughout the year and would advise on the reallocation of funds, as appropriate. An underspend was reported in 2022/23 and it was agreed that a summary would be provided to the Board on the reasons for the 2022/23 underspend. Communication would take place between budget holders, the Senior Leadership Team and finance to ensure opportunities for fund reallocation would be identified at the earliest opportunity. It was confirmed a data task and finish group had been established and were looking at performance data and updating the dashboard. It was confirmed that the dashboard would be presented to the Executive Team at the end of June. The Board welcomed the report and thanked the finance team for their involvement in the exercise. | GJ |
| Resolved | The Board: - agreed the methodology utilised in establishing the 2023-24 delegated budgets. - noted the financial framework as set out in the IMTP. - noted and considered the key risks and opportunities outlined, including the ongoing work to effectively manage the use of resources. - welcomed the development and improvements in data. |  |
| 1805/3.5 | “More Than Just Words” – Developing HEIW’s capacity |  |
|  | The Board received the report. In presenting the report, Dafydd Bebb provided an update on the additional resources allocated by HEIW to meet the actions assigned to the organisation by the Welsh Government’s More than Just Words Five Year Plan (MTJW Plan) and the National Workforce Implementation Plan (NWIP) in respect of Welsh Language. It was noted that MTJW and NWIP had allocated several actions to HEIW to support the improvement of the Welsh language skills of the NHS Wales workforce. The actions included HEIW taking on national roles for the first time in respect of the Welsh language to implement the numerous actions contained in both plans. HEIW was not established originally to undertake a national role in respect of Welsh Language and therefore additional capacity needed to be developed for the new responsibility. It was highlighted that three additional resources had been agreed by the Executive Team, one permanent role and two, two-year fixed term roles. A formal process was being undertaken to establish the roles pay scale bandings in line with national requirements. |  |
| Resolved | Members: - noted and supported the steps being taken to develop HEIW’s capacity to respond positively to the requirements of: - the More Than Just Words Five Year Plan and - the actions associated in respect of the Welsh Language by the National Workforce Implementation Plan. |  |
| PART 4 | GOVERNANCE, PERFORMANCE, AND ASSURANCE |  |
| 1805/4.1 | Finance Report |  |
|  | The Board received the report. Introducing the report, Glyn Jones updated the Board on the financial position reported for April 2023 (month 1) of the 2023-24 financial year. The report highlighted that there was an underspend of £2,421 as at 30 April 2023. Detailed work was being undertaken on the variances identified. The report highlighted that HEIW had a discretionary capital allowance of £88k for the year and proposals for the use of capital funding were being prepared. Further proposals were being developed, should additional capital funding become available during the financial year. It was noted that the target to pay 95% of all non-NHS invoices within 30 days was not met during 2022/23. Indicative figures for April 2023 showed that performance for both NHS and Non-NHS suppliers would be about 96.3% for the month. It was confirmed that a report would be provided to the Audit and Assurance Committee on the reasons for not meeting the target in 2022/23 and actions being taken to improve timely payment of suppliers. | GJ |
| Resolved | The Board: - noted the underspent financial position reported for HEIW at month 1. - noted that further proposals were being developed, in support of HEIW’s objectives, should financial resources become available in line with Board discussions. - noted the summarised explanation of key variations by Directorate. - noted the capital allocation and spend to date, and - noted the Balance Sheet position. |  |
| 1805/4.2 | Quarter 4 Performance Report |  |
|  | The Board received the report. In presenting the report, Alex Howells provided an overview of the performance for 2022/23. The report provided the highlights for each strategic aim, the financial position for each strategic position and performance and quality information for education and training internal organisational performance. Overall HEIW had achieved the majority of commitments and plans. The main challenge that affected organisation performance during the year related to the commissioned programmes for undergraduate nursing. It was confirmed that no areas were RAG rated as red. The Executive Team had discussed whether areas should be assessed as red or amber and decided areas that had been partially delivered, with no impact on overall performance and were not time critical should be assessed as amber. It was noted that the PADR completion rate was low, and conversations had taken place with teams to increase compliance. It was confirmed that upon reflection that PADR performance should have been RAG rated as red. It was confirmed that the mandatory training rate was 84% which was below the 85% target. It was recognised that HEIW had increased compliance in this area, however there was more to do to achieve the compliance rate. It was confirmed that there was minimum risk to the organisation due to the roles being undertaken. It was noted that the Board needed to be assured on performance across the organisation and that assurances needed to be provided on how the objectives contained within HEIW strategies were being implemented and delivered. The problems being seen with recruitment and retention onto courses in Higher Education Institutions had implications on commissioning and performance which related to risk 18 in the corporate risk register. It was highlighted that a task and finish group had been established to oversee implementation of the current year’s Education & Training Plan to ensure additional and clear focus on achieving fill rates. It was agreed that an exception report would be presented to the Board on work of the task and finish group in relation to commissioning dashboards, progress and findings. | SR |
| Resolved | The Board: - reviewed the report as an opportunity to provide assurance. - Identified risks, in line with the Education, Commissioning and Quality Committee, and welcomed the offer of an exception report being presented to the Board in July. |  |
| 1805/4.3 | NHS Performance Framework – Foundational Economy WG Bi-Annual Report |  |
|  | The Board received the report. In presenting the report, Glyn Jones outlined some of the key areas of HEIW’s progress in embedding the principles of the foundational economy during the period 1 September 2022 to 31 March 2023. It was confirmed that as part of the NHS Wales Performance Framework 2022/23, HEIW were required to report on progress in embedding the principles of the foundational economy. It was noted that updates were provided by Senior Responsible Officers on the actions implemented to support embedding of foundational economy principles. The reporting template highlighted four areas of focus. The second of two bi-annual updates was submitted to Welsh Government on 14 April 2023 following Executive Team approval. |  |
| Resolved | Board Members: - welcomed and noted the report submitted to Welsh Government. |  |
| 1805/4.4 | HEIW Climate Emergency National Programme Bi-Annual Reporting |  |
|  | The Board received the report. Introducing the report, Glyn Jones highlighted that the report outlined progress against the NHS Wales Decarbonisation Strategic Delivery Plan for the period 1 September 2022 to 31 March 2023. The report highlighted that the confidence rating of HEIW achieving a 16% reduction in emissions by 2025 against the NHS Wales 2018/19 benchmark continued to be amber. This had taken into account the further work required to understand HEIW’s carbon footprint and the opportunities for carbon reduction which were being finalised. It was noted that there was potentially more to be considered that was not currently captured within the actions in the report. For example, there were wider implications from the training and education commissioned by HEIW. It was highlighted that HEIW was actively looking at recruiting a volunteer to Chair the Green Group. |  |
| Resolved | Board Members: - noted the report submitted to Welsh Government. |  |
| 1805/4.5.1 | Key Issues Report – Education Commissioning and Quality Committee held on 23 March 2023 |  |
|  | The Board received the report. In presenting the report, Tina Donnelly highlighted the key issues raised at the Education Commissioning and Quality Committee meeting held on 23 March 2023. It was noted that a verbal update was provided at the last Board meeting in March and the written report paper was now being presented for consideration. It was noted that the Committee received the Medical, Dental and Pharmacy Directorates report and agreed for the report to be further adapted to include the GMC’s position on areas of increased risk. The Committee had also received the Nursing and Health Professional Report and agreed that a deep dive would be undertaken into attrition rates. |  |
| Resolved | The Board: - noted the content of the report from the Chair of the Education, Commissioning and Quality Committee. |  |
| 1805/4.5.2 | Key Issues Report – Audit and Assurance Committee held on 6 April 2023 and 3 May 2023 |  |
|  | The Board received the Key Issues report and the Audit and Assurance Committee Annual Report. In presenting the report, Gill Lewis highlighted the key issues raised at the Audit and Assurance Committee meeting held on 6 April 2023 and 3 May 2023. In the meeting which took place on 3 May 2023, the Committee received the Head of Internal Audit Report and Opinion 2023/23 and the Audit Wales Final Audit Plan and Audit Fee 2023/24. It was noted that Internal Audit was in the process of concluding two internal audits, IT Software/ Systems Development and SLA Arrangements. The time taken for management responses to be received to draft audit reports was RAG rated as red and an action plan was due to be presented to the Committee. Audit Wales had presented their Final Audit Plan and Audit Fee to the Committee. It was confirmed that fees had increased as a result of ISA315. The Committee requested further information regarding the scheduling of payments before approving the plan. The report highlighted that a Counter Fraud Risk Assessment was due to be presented at the next Committee and that Donna Macarthur had been appointed as a new Independent Member to the Audit and Assurance Committee. |  |
| Resolved | The Board: - noted the content of the report from the Chair of the Audit and Assurance Committee (Appendix 1 and Appendix 2) for assurance. - noted the content of the Audit and Assurance Committee’s Annual Report (Appendix 3). |  |
| 1805/4.6 | Governance Leadership and Accountability Standard |  |
|  | The Board received the report. In presenting the report, Dafydd Bebb highlighted that HEIW provided an account of its compliance with the relevant elements of the Corporate Governance Code within its Annual Governance Statement on an annual basis. It was noted that no departures from the Code were reported within the assessment. |  |
| Resolved | The Board: - considered and noted the assessment of the Board’s compliance with the Corporate Governance Code for assurance. |  |
| 1805/4.7 | Forward Work Programme |  |
|  | The Board received the report. In presenting the report, Dafydd Bebb highlighted that as part of the Standing Orders, the Board was required to approve its Forward Work Programme on an annual basis. It was noted that the Forward Work Programme set out a framework of the proposed work for the Board and for the Board Development Sessions in 2023/24. The Board welcomed the report and noted that the framework was subject to change depending on topics and issues identified throughout the year. |  |
| Resolved | Members: - approved the 2023/24 Board Forward Work Programme at Appendix 1 and for the Board Development Sessions at Appendix 2 and recognised that the Forward Work Programme was in transition and subject to change. |  |
| 1805/4.8 | Corporate Risk Register |  |
|  | The Board received the report which confirmed that there were eight risks on the Corporate Risk Register (CRR), of which, three had a red status, three an amber status, and two a green status. It was agreed that risk 18 would be reviewed and consideration given to its trajectory and the mitigations. | LL |
| Resolved | The Board: - noted the report for assurance |  |
| 1805/4.9 | In-Committee Decisions |  |
|  | The Board received the report which highlighted the key issues discussed at the In-Committee Board Meeting held on 30 March 2023 and 27 April 2023. |  |
| Resolved | The Board: - noted the report for information. |  |
| PART 5 | FOR NOTING |  |
|  | No papers for noting. |  |
| PART 6 | OTHER MATTERS |  |
| 1805/6.1 | Any other Urgent Business |  |
|  | The Board received a report on the Grant Award to Social Care Wales (SCW) to support Implementation of specific actions within the mental health workforce plan. In presenting the report, Glyn Jones highlighted that the Strategic Mental Health Workforce Plan for Health and Social Care was launched in late 2022. The plan contained a deliverable to complete year one of the plan in partnership with SCW and the Mental Health Network Board. It was highlighted that five actions within the plan had shared responsibilities with SCW and which required funding to be passed to SCW. Within the overall funding allocation, received by HEIW from Welsh Government, £3.37m was identified to implement the actions to be undertaken by SCW, during 2023/24 financial year. Therefore, the Board was asked to approve the transfer of £475k funding to SCW during the 2023/24 financial year, using the HEIW grant mechanism. In future years, arrangements would be made with Welsh Government to transfer appropriate funding directly to SCW. |  |
| Resolved | Members: - approved the transfer of funding of £475k to Social Care Wales (SCW) via the HEIW grant mechanism to contribute to the implementation of actions detailed in the Mental Health Workforce Plan, for the 2023-24 financial year. |  |
| 1805/6.2 | Dates of Next Meetings |  |
|  | The next meeting was confirmed as the HEIW Board Meeting to be held on Thursday 27 July 2023. |  |

.....................................................  	 	 	.............................

Chris Jones (Chair) 	 	 		 	Date: