Why is the project needed?

There are numerous key factors driving the need for a SWPPC, in particular significant workforce challenges impacting on the sustainability of primary care services. Drivers include:

- The previous workforce plan, developed in 2015, is now out of date

- Significant changes in workforce diversification since 2015 and no overarching plan to provide context for future workforce development

- Increasing sustainability issues across primary care due to recruitment and retention

- The current age profile of key professional groups (e.g. general practice nurses) critical to the effective delivery of primary care services

- The changing expectations of the workforce (increase in LTFT / flexible working patterns)

- Economic/financial impact on the delivery of care in specific areas (e.g. dental)​

- Global/national issues impacting future workforce (economic/social factors​; cost of living)

- Technological advances reshaping care (e.g. AI, predictive analytics, genomics)

- Changes in education and training standards; changing the shape of the future workforce

- Contract reform of independent contractor models in Wales

- Recovery from Covid-19, Immigration policy and the impact of Brexit.

Key deliverables:

Phase 1 – Initiation: Initial horizon scanning/research (Nov – Jan 23)

- Agree scope, establish governance arrangements, and complete project documentation

- Commence detailed stakeholder mapping and horizon scanning

- Develop data brief, communication, and engagement strategies

Phase 2 – Engagement and data (Feb – April 23)

- Commission and deliver engagement/communication strategies

- Analyse and conclude data

- Local/national consideration

Phase 3 – Shaping the plan (April - June)

- Shape an initial set of ideas and actions for wider testing with stakeholders

Phase 4 – Testing with stakeholders (July – August)

- Refine the plan and undertake consultation with key stakeholders across Wales.

- In parallel provide high level costings and implementation actions

Phase 5 – Finalisation and approval (Sept - Oct)

- Draft final plan

- Sign off the final plan and develop implementation framework aligned with IMTP planning cycle

Phase 6 – Implementation planning – details to be confirmed.

C

What is the scope of the project?

In scope includes:

- The delivery of primary care services at a practice, cluster or other geographical footprint including those delivered through independent contractors, managed practices or health board employed models

- The workforce needed to deliver primary care to vulnerable groups such as those within the prison population, or where there are particular barriers for vulnerable groups in accessing care

- The workforce needed to deliver urgent primary care including first contact clinical services (such as those delivered by the 111 service and GP Out of Hours)

To prevent replicating work being undertaken elsewhere, the scope does not include:

- Social care, 999 services and the delivery of services by independent and third sectors.   However, it is recognised that these services are important within the bigger context and alignment will therefore need to be continually tested as part of the development of the plan, in particular alignment with the AHP framework.

Outcome/success criteria:

- Understand current demand drivers. Identify key factors shaping demand for the next 10 years

- Understand technological advances and fast approaching changes in healthcare delivery

- Identify challenges and key supply-side issues across professional groups and areas of Wales to create a framework for future supply pipelines

- Present recommendations to support the development of a sustainable workforce model to take forward the delivery of the Primary Care Model for Wales

- Recognise the interface and delivery of the broad range of services aligned with primary care,  and how any changes to primary care workforce models will impact these

- Provide a clear framework for local, regional, and national action to underpin decisions on education and training commissioning.

Timescale for delivery: 12 months in line with IMTP 2024/25

Phase 1 – November 2022 – January 2023

Phase 2 – February – April 2023 (mindful of Easter break)

Phase 3 – April – June 2023

Phase 4 -  July – August 2023 (mindful of school holidays/summer period)

Phase 5 – September – October 2023 (NPCB sign off November 2023)

Phase 6 – dates to be agreed.

Who will deliver this project?

DPCC Lead: Chris O’Connor – Interim Director of Primary Care and Mental Health (ABUHB)

Project Lead: Dorothy Edwards – Programme Director, National Programmes (HEIW)

Project Workforce Lead: Abi Powell – Primary Care Workforce Lead/ Project Manager (HEIW)

Project Manager: Samantha Jeffries – Project Manager (SPPC)